2012/2013 DRAFT IDP DOCUMENT

[

IDP  FOR   2012/2013

INDEX

|  | CHAPTER 1: PLANNING PROCESS | Page | 4 |
| --- | --- | --- | --- |
|  | Introduction and background | Page | 5 |
|  | Contents | Page | 6 |
|  | Municipal Mandate, Powers and Functions | Page | 8 |
|  | The Process Plan | Page | 9 |
|  | IDP framework | Page | 11 |
|  | Summary of Public Participation Process | Page | 12 |
|  | CHAPTER 2: SITUATION ANALYSIS | Page | 13 |
|  | Current Reality: Basic facts and figures | Page | 13 |
|  | Summary of Municipal Priority Issues | Page | 17 |
|  | Spatial Analysis | Page | 18 |
|  | Social Analysis | Page | 19 |
|  | Economic Analysis | Page | 26 |
|  | Institutional Analysis | Page | 29 |
|  | Priority Issues in Context | Page | 31 |
|  | CHAPTER 3: OBJECTIVES & STRATEGIES | Page | 33 |
|  | The Municipal Strategy Framework | Page | 34 |
|  | CRDP | Page | 36 |
|  | GANTT CHART CRDP | Page | 37 |
|  | EPWP | Page | 45 |
|  | Mayoral Poverty alleviation Programme | Page | 47 |
|  | Alignment with the Municipal Performance Management System | Page | 50 |
|  | Municipal Vision | Page | 52 |
|  | Municipal Performance Objectives | Page | 54 |
|  | Basic Service Delivery and Infrastructure Investment | Page | 54 |
|  | Local Economic Development | Page | 74 |
|  | LED Projects | Page | 75 |
|  | Municipal Institutional Transformation and Development | Page | 80 |
|  | Good Governance and Public Participation | Page | 81 |
|  | CHAPTER 4: PROJECTS | Page | 84 |
|  | Basic Service Delivery and Infrastructure Investment | Page | 85 |
|  | Local Economic Development | Page | 118 |
|  | Municipal Institutional Transformation and Development | Page | 121 |
|  | Good Governance and Public Participation | Page | 123 |
|  | PROJECTS :Aligned to the budget | Page | 124 |
|  | PROJECTS: Sector Departments Programmes | Page | 134 |
|  | PROJECTS : Unfunded | Page | 150 |
|  | SLP PROJECTS | Page | 159 |
|  | Running Projects | Page | 162 |
|  | CHAPTER 5: INTEGRATION | Page | 166 |
|  | Operational Strategies and Programme Integration | Page | 167 |
|  | Water Sector Plans | Page | 167 |
|  | Financial Plan for Municipality | Page | 168 |
|  | 3 Year Capital Investment Programme | Page | 174 |
|  | Monitoring & Performance Management System | Page | 175 |
|  | Spatial Development Framework | Page | 175 |
|  | Integrated Poverty Reduction & Gender Equity Programme | Page | 176 |
|  | Integrated Environmental Management Programme | Page | 176 |
|  | Integrated Local Economic Programme | Page | 176 |
|  | Integrated Institutional Programme | Page | 179 |
|  | Integrated HIV/ Aids Programme | Page | 181 |
|  | Disaster Management Plan | Page | 181 |
|  | Waste Management Plan | Page | 181 |
|  | Transport Plan | Page | 181 |

PLANNING PROCESS

CHAPTER  1

  - The Planning Process

1.1.1	Introduction and Background

This is the new version of Joe Morolong IDP Plan, a strategic document that will guide the development processes in the 2012/2013 financial year. During the first term of governance Joe Morolong was identified as one of the presidential nodal points in the country, which is now in this third term known as CRDP, this municipality was faced with serious challenges in addressing backlogs regarding basic services, i.e. water, sanitation, roads, electricity and refuse removals. To a certain extend the municipality did not manage to reach its targets due to certain challenges such as lack of proper planning, implementation and monitoring of projects, insufficient funding for municipal programmes and projects, shortage of staff, and lack of enough departmental guidelines, support and framework towards ensuring that our IDPs addresses the real needs of our people.

intergovernmental team led by the Presidency and the Department of Provincial and Local Government, decisions by the President’s Coordinating Council regarding the nature, role and format of the IDP, IDP Hearings, meetings and workshops held in preparations for the development of credible IDPs and guidance for District Municipality’s Growth and Development Summits.

However, for these guidelines to be of any value within the unique context of our municipality, an awareness and understanding of other strategic documents that complement the developmental processes are indeed required. Such strategic documents will among others be the Provincial Growth and Development Strategy (PGDS) the National Spatial Development Perspective (NSDP), Sector Plans, projects and Programmes prepared for specific areas, proposals of parastatals for the rollout and maintenance of existing infrastructure in our areas and proposals of private sectors for development of our areas. It is then only within the developmental context that these guidelines can be given appropriate, local meaning and be put into practice.

Furthermore, the municipality need to comply with various sets of legislation and policies governing municipalities.  One such set of legislation is the Municipal Systems Act and its regulations. According to this Act, all Municipalities need to compile an Integrated Development Plan (IDP), Section 25 (a)

“Each municipal council must, within the prescribed period after the start of its elected term, adopt a single, inclusive and strategic plan for the development of the municipality which links, integrate and co-ordinates plans and take into account proposals for the development of the municipality”. That strategic plan will then be reviewed annually according to Section 34 (a)

“A municipal council must review its integrated plan annually in accordance with an assessment of its assessment measurements”.

In the light of the above, Joe Morolong local Municipality is presenting its Integrated Development Plan as from 2012/2013. This strategic document will be used as a tool to guide the development process in order to ensure sustainable development through capacity building, basic service delivery, eradication of poverty, creation of wealth through Local Economic Development and enabling the inter and intra governmental cooperation.

In conjunction with the District Integrated Development Plan, Joe Morolong Local Municipality will further present its first draft IDP as its principal strategic planning instrument which will guide and inform the development process, budget, management and decision making during the 2012/2013 financial year. This draft has been prepared through the proper channels of consultation process as indicated in the Municipal Systems Act and the IDP Guide Packs. And it is also trusted that what contains into this document is indeed the true reflection in regard to the needs of the people of Joe Morolong especially looking at their developmental priorities for the 2012/2013 financial year.

In conclusion, Joe Morolong Municipality would like to appreciate the contributions made by all stakeholders that were involved during this processes and we also like to commit ourselves to implement projects and programmes contained into this document to ensure a better life for all. This plan should not be seen as a set of unrealistic dreams and wishes but as an action plan towards sustainable developments which are realistic and achievable.

1.1.2	Contents

This document will focus in two cornerstones of local government, i.e. the support, subsistence and inclusive local economies and the development of sustainable human settlement in all their dimensions. These should further be developed based on the following two key components:

- Long term component and

- 1 year implementation programme

The long term framework will be consist of a mission & vision, set of objectives and strategies that provides guidance and direction to the five year implementation programme of the elected council for its term of office.

This planning document will also be made up of phases,

i.e. phase one to phase four.

- PHASE 1 : OUTPUTS

      - Vision

      - Mission

      - Objectives

      - Strategies

      - Identified projects

- Phase 2 : OUTPUTS, PERFORMANCE INDICATORS

      - Project Outputs

      - Targets

      - Location

      - Project Related Activities

      - Time Schedule

      - Costs Estimates

      - Budget

- PHASE 3 : OUTPUTS

      - Three Year Financial Plan

      - Three Year Capital Investment Plan

      - Water Sector Plan

      - Housing Sector Plan

      - Integrated SDF

      - LED Strategy

      - Consolidated Monitoring / Performance Management System

      - Skills Development Plan

      - Disaster Management Plan

      - Waste Management Plan

      - Transport Plan

      - Employment Equity Plan

- PHASE 4 : OUTPUTS

      - Approval

      - Adoption

1.1.3	Municipal Mandate, Powers and Functions

The mandate of the municipality as contained in section 152 of the constitution is

- To provide democratic and accountable government for local communities

- To ensure the provision of services to communities in a sustainable manner

- To promote social and economic development

- To promote a save and healthy environment

- To encourage the involvement of communities and community organizations in the matters of local government

This policy statement guides the formulation and implementation of the integrated development plan and therefore every decision and action of the municipality.

In regard to powers and functions, the municipality is currently not performing all functions and powers as supposed to. The following are performed by the municipality.

- Cemeteries

- Municipal planning

- Local Tourism and LED

- Sanitation

- Local Sports Facilities

- Municipal Roads

- Street Lighting

- Water Reticulation

- Operation and Maintenance of water

- Building Regulations

The following are also allocated to the municipality but not performed; we are in the process of developing by-laws that will enable us to regulate these functions-

- Air Pollution

- Noise Population

- Local Amenities

1.1.4	The Process Plan

The IDP Process Plan is a preparatory work that needs to be done prior to the commencement of the planning process. It has to be developed in a form of a document which should contain the following:

- Institutional structures for the management of the process

- Approach to public participation

- Structures for public participation

- Time schedule for the planning process

- Roles and responsibilities (Who will do what) and

- How the process will be monitored.

This plan also serves to address one of the legislative requirements, section 16 (i) which states,

“a Municipality must develop a  culture of municipal governance that complements formal representative government with

a system of participatory governance and must for  this purpose-

(a) encourage and create conditions for the local community to participate in the affairs of the Municipality, including the-

(i)   preparations, implementation and review of its Integrated Development Plan”.

- Detailed Activity Plan for finalising the draft IDP

| Required Outputs |  | BY WHOM | Period (final date for completion) |
| --- | --- | --- | --- |
| 1 | Preparation for IDP and budget process plan for approval by council | CFO and IDP manager | 10 August 2012 |
| 2 | Preparation for IDP review process by communicating to IDP forum stakeholders | HOD | 3 to 10 Sept 2012 |
| 3 | First IDP meeting with all stakeholders | MAYOR/IDP MANAGER. | 10 Sept 2012 |
| 4 | Inputs for projects for all stakeholders (2013/2014) | IDP manager | 12 to 13 Sept.2012 |
| 5 | Second IDP meeting with all the stakeholders | IDP manager | 30 Sept.2012 |
| 6 | First draft budget and policies to council for 2013/14 | CFO/Municipal Manager | 30 October 2012 |
| 7 | Submission of a draft IDP to council | IDP Manage/HOD | 25 Nov. 2012 |
| 8 | Comparison between 2012/13 IDP initiatives originating from the strategic planning session. | All the Departments. | 05 TO 09November 2012 |
| 9 | Formulation of key IDP Priorities for 2013/2014 | All departments | 12 to 16 November 2012 |
| 10 | Prepare and distribute departmental total budgets MTEF to all heads of departments with actual figures and distribute the budget guidelines received from national treasury to all heads of departments. | CFO/Acc.Expenditure | 16 November 2012 |
| 11. | Meeting with heads of departments for budget compilation | CFO | 19 November 2012 |
| 12 | Adjustments of all grants gazetted for MTEF as per DORA | CFO | 21 November 2012 |
| 13 | Community Consultation/participation on the draft of the IDP | IDP MANAGER | 22 November 2012 |
| 14 | Meeting with heads of departments for budget compilation | CFO | 6 December 2012 |
| 15 | Align total budget with IDP with National and provincial priorities and Growth and Development Plan | All the departments | 13 January 2013 |
| 16 | Presentation of a Draft IDP 2013/2014 | council | 26February 2013 |
| 17 | Commence public budget IDP participation process with all wards within Joe Morolong Local Municipality | CFO/IDP(Chairpersons) | April 2013 |
| 18 | Presentation of public participation results to Council for inclusion into the final budget of 2013/14 | Mayor/CFO/IDP | April 2013 |
| 19 | Final total budget proposal to council for approval | Mayor/CFO/IDP | 31 May 2013 |
| 20 | Finalisation of departmental SDBIPs | HODs | 4 June 2013 |
| 21 | Finalisation of municipal SDBIPs | MM | 18 June 2013 |
| 22 | Send approval budget to provincial and national treasury | CFO/MM | 25 June 2013 |

1.1.5	IDP Framework

As part of the preparation stage, the district council in consultation with its local municipalities must adopt a framework for Integrated Development Planning. That framework will determine the procedures for coordination, consultation and alignment between the district and local municipalities. It also supposes to guide municipalities in preparing its process plans.

Development of this Framework is also one of the compliances as stipulated in the Municipal System’s Act, Section 27 (2)

“a framework referred to in subsection 1 binds both the district and local municipalities in the area of a district municipality, and must at least –

(a) identify the plans and planning requirements binding in terms of national and provincial legislation on the district municipality and the local municipality or on any municipality.

(b) identify the matters to be included in the IDP of the district and local municipalities that require alignment.

(c) specify the principles to be applied and coordinate the approach to be adopted in respect of those matters and

(d) determines procedures.”

1.1.6	Summary of the Public Participation Process

A proper and well-planned public participation process, as set out in the Process Plan (IDP Guidelines) and in accordance with the section 16 of the Municipal Systems Act, is always followed, not only for the first round of IDP but also during all annual review processes.

During the Analysis Phase, Councilors went out to their various constituencies, meeting with the communities assisted by their ward committee members.  Priority issues based on the community needs were determined in this way, traditional leaders were also involved.  This exercise proofed to be very fruitful and resulted in the Councilors being the link between the community and the Municipality.  This process was followed during the whole IDP process.  During the Review Process the “Steering Committee” and Representative Forum as main participants, formed the link with the community. The existing IDP document was then developed, scrutinized, shortfalls identified, necessary amendments made etc. in order to produce a more realistic, but inclusive IDP, hence the development of this document.

Councillors also participated in all the necessary alignment, strategy and project team training workshops during the first round of planning.  A vision and appropriate objectives were also formulated at “open” workshops.  The responsibility to continue informing the community and getting inputs from the community after each of these workshops were that of the Councillors.

Please note that although the participation process was quite elaborate and fruitful, the Municipality recognized that it was not at all times successful.  However, it is in the process of rectifying the mistakes that were made and is in the process of ensuring that participation remains the driving force behind its efforts to become more developmental orientated.

One of the mistakes that were rectified was the establishment of a properly functional IDP Steering Committee, which consists of the Municipal Manager, IDP Manager and Senior Managers.

2.1	Current Reality: Basic facts and figures

The purpose of the situation analysis is to determine the current reality in the Joe Morolong Local Municipality. This analysis would provide basic facts and figures regarding priority issues in the Municipality. This would provide guidance in respect of the development needs in the Municipality, and therefore the framework for the formulation of strategies in Chapter 3. The analysis would also provide the basis for the identification of projects that the Municipality will invest in to ensure implementation of the identified strategies.

Figure: Situation analysis in context of the integrated IDP formulation process

The analysis contained in this Chapter would centre on the following focus areas:

- Summary of community and stakeholder priority issues.

- Spatial Analysis.

- Social Analysis.

- Economic Analysis.

- Institutional Analysis.

- Priority Issues in Context.

Table: Statistical Overview: Water provision in the Joe Morolong municipal area

| No Access to Pipe | 6,002 |
| --- | --- |
| Pipe water(dwell) | 241 |
| Pipe water( yard) | Acceptable level of access; 24 938; 61.49%. Insufficient level of access; 15 617; 38.51%. 1,044 |
| Pipe water<200m | 6,578 |
| Pipe water>200m | 6,414 |
| Regional Local Scheme | 11,073 |
| If the state of water provision in the municipal area is analysed, it is clear that the majority of the population enjoys safe and acceptable standards of access to water. However, water provision remains a challenge to the Municipality (and its number one priority). Borehole | 4,928 |
| Spring | 808 |
| Rain-water tank | 171 |
| Dam/pool/stagnant | 1,825 |
| River/stream | 1,184 |
| Water vendor | 228 |
| Other | 59 |
| Not Applicable Src | 0 |
| Not Applicable Pipe | 0 |
| Villages with water reticulation | 160 |
| Villages with water reticulation backlog | 26 |
| Estimated current cost to eradicate the reticulation backlog | R 78 million |

(Partly from www.demarcation.co.za)

| Removed once week | 36 | 0.18% |
| --- | --- | --- |
| Removed less often | 23 | 0.11% |
| Communal dump | 529 | 2.61% |
| Own refuse dump | 17054 | 84.10% |
| No Disposal | 2636 | 13.00% |
| Not Applicable | 0 | 0.00% |

Statistical Overview: Sanitation

| Removed once week | 36 |
| --- | --- |
| Removed less often | 23 |
| Communal dump | 529 |
| Own refuse dump | 17,054 |
| No Disposal | 2,636 |
| Not Applicable | 0 |

(Source: www.demarcation.co.za)

Table: Energy source: Cooking 			Table: Energy source: Heating			Table: Energy source: Lighting

| Electricity | 1,649 |
| --- | --- |
| Gas | 1,655 |
| Paraffin | 2,786 |
| Wood | 12,807 |
| Coal | 40 |
| Animal dung | 1,298 |
| Solar | 17 |
| Other | 25 |
| Not Applicable | 0 |

Sanitation remains a serious concern and challenge for the Municipality; especially if it is considered that only 0,18% of the population have access to weekly refuse removal services.

| Electricity | 6,958 |
| --- | --- |
| Gas | 18 |
| Paraffin | 1,580 |
| Candles | 11,603 |
| Solar | 34 |
| Other | 85 |

| Electricity | 1,485 |
| --- | --- |
| Gas | 352 |
| Paraffin | 2,058 |
| Wood | 14,845 |
| Coal | 86 |
| Animal dung | 1,199 |
| Solar | 13 |
| Other | 238 |
| Not Applicable | 0 |

Good progress has been made over the last couple of IDP cycles to provide electricity to households in the Joe Morolong municipal area. The demand for high mast lighting from the community remains a challenge for the municipality, however; especially in light of the high cost of these lights.

The lack of sufficient public transportation in a vast area (such as that of the Joe Morolong municipal area) remains a challenge; especially since this is not a Constitutional core function of the Municipality.

Statistical Overview: Transportation

| Not applicable | 54,601 |
| --- | --- |
| On foot | 34,035 |
| Bicycle | 174 |
| Motorcycle | 25 |
| Car as a driver | 326 |
| Car passenger | 721 |
| Minibus/taxi | 461 |
| Bus | 1,273 |
| Train | 37 |

(Source: www.demarcation.co.za)

2.1.1	Summary of Municipal Priority Issues

Being the third round of IDP for this Municipality, it is still very important for the Council to continue identifying the needs of its residents and the trends pertaining to facts and figures. It therefore embarked on an intensive participation process whereby individual ward councillors and ward committees met in order to prioritise needs or issues received from each ward.  It also investigated the basic facts and figures of the Municipality, of which the results are available in the Existing Information and Municipal Level Analysis document.  Results from these two processes were compared, leading to the identification of 10priority issues for Joe Morolong for the period 2012 to 2013.

- Proper water supply system and the upgrading of sanitation and sewerage system: Residents, households and in some cases whole villages lack easy access to proper drinking water supply systems and proper sanitation and sewerage systems, affecting the community’s health.

- Upgrading of existing and construction of new roads: Poor condition of gravel roads and total lack of proper main, access and internal roads. Also insufficient road system catering for a vast area.

- Housing: Shortage of proper and sufficient housing for all.

- Institutional development and land use management: Inadequate financial and administration management in Joe Morolong Municipality, due to the lack of enough capacity.

- Recreation facilities: No access or poor condition of recreation facilities in most of the wards.

- LED projects: Lack of enough job opportunities and skill development to combat the high rate of unemployment.

- Cemeteries: Poor conditions of cemeteries and the lack of access road, fencing, toilets and water on grave yards.

- Public transport improvement: Lack of or insufficient public transport system in a vast area.

- Disaster management

- Waste management (Environmental issues): Poor optimisation, preservation and the sustainable utilisation of natural resources

2.1.2	Spatial Analysis

The jurisdiction area of Joe Morolong municipality is located in the Northern Cape Province in John Taolo Gaetsewe Region. The municipal area is approximately 5 813 km2 in size. This area is characterized by mainly rural establishments made up of 187 villages of different sizes and numerous scattered villages connected by gravel and dirt roads. Various Tribal Authorities exist with nine Paramount Chiefs within this municipal boundary and the municipality is entirely a municipal land, a real challenge. It has a population of 100 639 in 2001 which decreased to 92 998 in 2010 the overall decrease % was of 0.87, with 187 villages, 19698 households, 168 schools, 5 police stations, 25 clinics and 2 community health centers.

POPULATION PROFILE: For Joe Morolong Local Municipality,2001 - 2010

| RACE | MALE | FEMALE | TOTAL |
| --- | --- | --- | --- |
| AFRICAN | 44010 | 46525 | 90536 |
| WHITE | 574 | 451 | 1025 |
| COLOURED | 738 | 677 | 1415 |
| ASIAN | 8 | 13 | 21 |
| TOTAL | 45331 | 47666 | 92998 |

Source:Global insight,2011

The Joe Morolong Local Municipality is part of the John Taolo Gaetsewe District. The Municipality comprises an area of 6,030,000 hectares and includes 187 villages. The Joe Morolong Local Municipality faces far-reaching and, in some instances, even desperate service delivery challenges. This became evident from an analysis of available statistical records of the area. In this regard, the results of Census 2001, read in conjunction with the results of the Community Survey conducted in 2007 would be utilized to analyze the environmental demands facing the Municipality, and the strategies that it has adapted to respond to these demands.

Map 2: Joe Morolong Municipal Area

A total of 97.76% of the population of the area has been born in South African, and 0,10% in other SADC countries.

A total of 20,15% of the 22,277 households consists of only one person, 10,25% of three persons, 11,14% of four, 10,41 of five and 9,23% of only two. However, 29,83% consists of six and more persons.

A total of 95,57% of the population speaks Setswana as 1st language.

(Source: www.demarcation.co.za)

Table:  Population in relation to municipal area

| Population | 106,103 |
| --- | --- |
| Municipal Area | 6.030.000 hectare 9 477,456 km2 |
| Villages | 187 |
| Number of registered indigents | 8 014 |

Joe Morolong is characterised by a high density rural population, which is poorly served and poorly connected to the main stream of economic activities. There is a high level of unemployment with a dependency on subsistence agriculture, the public sector, seasonal workers and employment in the mining sector. Joe Morolong is being identified as a Comprehensive Rural Development Programme, (CRDP)

2.1.3	Social Analysis

The social analysis contained in this section would concentrate on analysing the opportunities and threats for the Municipality that originate from the social factors:

- Basic social indicators; including racial distribution, age distribution and gender distribution of the population.

- Some basic statistics regarding housing. In this regard, the number of occupied rooms and tenure status of the population would be considered.

- Access to public amenities.

- HIV/Aids Prevalence.

- Education.

- Access to transport.

Figure / Table: Racial distribution of the population

| Black African | 90536 |
| --- | --- |
| Coloured | 1415 |
| Indian or Asian | 21 |
| White | 1025 |

Figure / Table: Gender distribution of the population

| Female | 46525 |
| --- | --- |
| Male | 44010 |

Figure / Table: Age breakdown of the Joe Morolong Population

| 0-4 | 11 949 |
| --- | --- |
| 5-9 | 1 276 |
| 10-14 | 14 038 |
| 15-19 | 10 994 |
| 20-24 | 7 460 |
| 25-29 | 5 271 |
| 30-34 | 4 419 |
| 35-39 | 4 282 |
| 40-44 | 4 079 |
| 45-49 | 3 471 |
| 50-54 | 2 699 |
| 55-59 | 2 353 |
| 60-64 | 2 099 |
| 65-69 | 1 831 |
| 70-74 | 1 413 |
| 75-79 | 961 |
| 80 and over | 1 104 |

(Source: Global insight 2011)

Table / Figure: Persons with disabilities

| No disability | 84 455 |
| --- | --- |
| Sight | 2 361 |
| Hearing | 949 |
| Communication | 206 |
| Physical | 1 446 |
| Intellectual | 367 |
| Emotional | 869 |
| Multiple | 1 051 |

(Source: global insight 2011)

The composition of the population of the Joe Morolong municipal area has implications in a variety of areas and concerns. The first is the obvious need for the Municipality to respond to service delivery in terms of Government’s policy framework for the upliftment of previously disadvantaged communities. In this regard, target groups would include women, black members of the community, the youth and persons with disabilities. The second implications of the composition of the population are in terms of the composition of the staff establishment of the Municipality.

All the employees of the Municipality are presently black, with the main challenge in terms of employment equity to ensure increased access to employment opportunities to persons with disabilities and women. However, the skill shortage in the population area makes the achievement of these targets difficult.

The Municipality addresses the demands of its population dynamics in terms of its Special Programmes initiatives, which deal with the promotion of the interests of targeted groups, such as youth development, women development and programmes aimed at promoting the interests of persons with disabilities.

Table: No. of rooms				Table: Tenure status

| One | Owned,Fully Paid; 17 637. Owned,Not Paid; 386. Rented; 763. Occupied rent-free; 1 208. Not applicable; 285. 2 580 |
| --- | --- |
| Although Constitutionally not a municipal core function, the Joe Morolong Municipality has acknowledge housing as a priority concern, and has engaged in various initiatives to strengthen the hands of the Northern Cape Provincial Government in providing housing to the local community. Two | 3 989 |
| Three | 3 279 |
| Four | 3 157 |
| Five | 2 267 |
| Six | 1 868 |
| Seven | 1 259 |
| Eight | 736 |
| Nine | 405 |
| Over Ten | 451 |
| Not Applicable | 282 |

(Source: www.demarcation.co.za)

Statistical Overview: Access to Housing

| House or brick structure on a separate stand or yard | 12,485 |
| --- | --- |
| Traditional dwelling/hut/structure made of traditional materials | 6,676 |
| Flat in block of flats | 42 |
| Town/cluster/semi=detached house (simplex; duplex; triplex) | 49 |
| House/flat/room in back yard | 34 |
| Informal dwelling/shack in back yard | 212 |
| Informal dwelling/shack NOT in back yard | 439 |
| Room/flatlet not in back yard but on shared property | 41 |
| Caravan or tent | 18 |
| Private ship/boat | 0 |
| Not applicable (institution) | 286 |

(Source: www.demarcation.co.za)

Statistical Overview: Access to public enmities

| Number of clinics | 27 |
| --- | --- |
| Number of health centres | 3 |
| Number of libraries | 2 |
| Number of community halls | 12 |
| Number of police stations | 5 |

It must be accepted that the pattern expressed in the National Spatial Development Perspective (NSDP), namely that the spatial patter of the national spatial economy will remain static, and dominated by the metropolitan areas and their immediate surroundings. This implies that the economic growth potential of the Joe Morolong Local Municipality will in all likelihood be limited for the foreseeable future.

This situation is worsened by the apparent trend identified in the NSDP, namely that, in terms of the poverty gap and unemployment have shown trend to worsened in key localities, especially in rural districts. It must be accepted that this trend will be reflected in the Joe Morolong municipal area as well.

Although no specific statistics is available to focus on the HIV/Aids prevalence rate in Joe Morolong Municipality, a relevant trend analysis could be made by looking at trends in the North West (in which jurisdiction the Municipality previously felled) and the Northern Cape; These are as follows:

Figure / Table: HIV/Aids Prevalence

| Province | 2001 prevalence % | 2002 prevalence % | 2003 prevalence % | 2004 prevalence % | 2005 prevalence % | 2010 prevalence % |
| --- | --- | --- | --- | --- | --- | --- |
| North West | 25.2 | 26.2 | 29.9 | 26.7 | 31.8 | 32 |
| Northern Cape | 15.9 | 15.1 | 16.7 | 17.6 | 18.5 | 15.6 |

|  |  |  | North West | Northern Cape |
| --- | --- | --- | --- | --- |
|  | North West | Northern Cape | Year-on-year growth / decline | Year-on-year growth / decline |
| Y2005 | 25.2 | 15.9 |  |  |
| Y2006 | 26.2 | 15.1 | 3.97% | -5.03% |
| Y2007 | 29.9 | 16.7 | 14.12% | 10.60% |
| Y2008 | 26.7 | 17.6 | -10.70% | 5.39% |
| Y2009 | 31.8 | 18.5 | 19.10% | 5.11% |
| Y2010 | 29 | 15.6 | -8.81% | -15.68% |

(Source: http://www.avert.org/safricastats.htm)

It could be accepted that the growing trends reflected above is similar for and equally applicable to the Joe Morolong municipal area.

Similar to most rural area in the country, the Joe Morolong local area faces severe challenges in educating its population, as is reflected in the following statistics:

Table: Highest qualifications amongst the population of Joe Morolong

| No schooling | 8992 |
| --- | --- |
| Grade 1/Sub A | 6 263 |
| Grade 2/Sub B | 4 729 |
| Grade 3/Std 1 | 6 487 |
| Grade 4/Std 2 | 6 568 |
| Grade 5/Std 3 | 6 032 |
| Grade 6/Std 4 | 5 958 |
| Grade 7/Std 5 | 5 518 |
| Grade 8/Std 6 | 4 474 |
| Grade 9/Std 7 | 3 571 |
| Grade10/Std 8/NTCI | 2 981 |
| Grade11/Std9/NTCII | 2 773 |
| Grade12/St10/NTC3 | 6628 |
| Cert.noGrade12 | 2186 |
| Dip.noGrade12 | 44 |
| Cert.withGrade12 | 866 |
| Dip.with Grade12 | 699 |
| Bachelor's degree | 199 |
| B Degree,dip | 41 |
| Honour's degree | 199 |
| Higher degree | 199 |
| Not applicable | 11 949 |

(Source: global insight 2011)

2.1.5	Economic Analysis

The Joe Morolong Local Municipality is faced with severe economic challenges. The area is poverty-stricken and faces harsh realities of chronic unemployment and a huge dependency on government grants. This analysis would subsequently concentrates on the following manifestations of the economic conditions in the Municipality:

- Occupation trends.

- The extent of unemployment in the area.

- Personal income levels of the population.

- Household income.

Table: Main occupations

| Senior Officials | 406 |
| --- | --- |
| Professionals | 511 |
| Tech/Assoc Prof | 511 |
| Clerks | 197 |
| Service workers | 503 |
| Skilled agric work | 845 |
| Other | 462 |
| Elementary occupations | 586 |
| Occupations NEC | 69 |
| Plant Operators | 387 |

Figure / Table: Extent of unemployment in the Joe Morolong municipal area

| Employed | 4 451 |
| --- | --- |
| Unemployed | 6 420 |
| Not Economically Active | 36 617 |

(Source: www.demarcation.co.za)

| No income | 7 781 |
| --- | --- |
| R1 - R4 800 | 2 322 |
| R4 801 - R 9 600 | 4 959 |
| R9 601 - R 19 200 | 2 805 |
| R19 201 - R 38 400 | 1 446 |
| R38 401 - R 76 800 | 681 |
| R76 801 - R153 600 | 208 |
| R153601-R307200 | 34 |
| R307201-R614400 | 5 |
| R614401-R1228800 | 6 |
| R1228801-R2457600 | 23 |
| R2 457 601 , more | 2 |
| Not Applicable | 3 |

| Table / Figure: Personal income No income | 7 781 |
| --- | --- |
| R1 - R4 800 | 2 322 |
| R4 801 - R 9 600 | 4 959 |
| R9 601 - R 19 200 | 2 805 |
| R19 201 - R 38 400 | 1 446 |
| R38 401 - R 76 800 | 681 |
| R76 801 - R153 600 | 208 |
| R153601-R307200 | 34 |
| R307201-R614400 | 5 |
| R614401-R1228800 | 6 |
| R1228801-R2457600 | 23 |
| R2 457 601 , more | 6 |
| Not Applicable | 3 |

Table / Figure: Household income  2010

| No income | 73 805 |
| --- | --- |
| R0 – R2400 | 36 |
| R2400—R12000 | 1620 |
| R12000—R30000 | 5121 |
| R30000—R54000 | 5150 |
| R54000—R96000 | 3530 |
| R96000—R192000 | 2266 |
| R192000—R360000 | 1111 |
| R360000---R600000 | 482 |
| R600000—R1200000 | 273 |
| R1200000—R2400000 | 85 |
| R2400000 + | 24 |

(Source: Global insight 2011)

2.1.6	Institutional Analysis

The main disadvantages for the Joe Morolong Local Municipality, in terms of its institutional capacity, are:

- The rural and remote location of the municipal area; and

- The poverty-stricken population; resulting in a almost complete lack of own revenue, and huge dependency on government grants.

The Municipality has nevertheless been awarded the Vuna Awards in 2008 for the most improved Municipality in the Northern Cape; reflecting its determination to built a winning Municipality and community, in spite of severe challenges.

Figure: The political top structure of the Joe Morolong Local Municipality

Figure / Table: Summary of the Municipal staff establishment

| Number of posts | 151 |
| --- | --- |
| Vacancies | 42 |
| Filled during the 2011/12 financial year | 5 |
| Vacant funded posts | 14 |

Figure: Administrative Top-structure of the Municipality

The high unemployment rate in the municipal area causes a long-term capacity problem, in terms of its restrictive result on access to education and skills development. The result is that limited capacity is generated in the community to appoint persons with sophisticated skills and competencies required to achieve the strategic goals and objectives of the Municipality and give practical effect to the core functions for which it is responsible.

The high percentage of persons employed in elementary occupations in the area further confirms the employment and skills patterns in the Joe Morolong community. The result is that the Municipality is forced to “import” a high percentage of the specialised skills and competencies required to achieve its goals and objectives. The Municipality is seldom able of retaining these skills because of the rural nature of the area and the incapability of the institution to offer competitive remuneration packages.

Table: Comparative strengths and weaknesses of the municipal institution

| Strengths |  | Weaknesses |
| --- | --- | --- |
| - Municipality founded out of nothing - Allow own initiative and drive processes - Opportunity to be courageous and developmental - Able to recruit young, qualified people - Managers willing to work as a team toward common goals - Newly established bursary scheme for officials - Opportunity to explore and expand knowledge and skills |  | - Lack of scares skills - Lack of resources: result in unemployment - Equitable share allocation not reflective of development needs - Working situation- employees must travel long distances to and from work, without proper remuneration - Competitive salaries - Grading of municipality - Understanding of roles between traditional authorities and municipality - Not a tax-based municipality; does not generate own revenue |

Financial viability remains a major challenge for the Municipality. Its almost complete and total dependency on grants and the lack of own revenue reduces the Municipality’s capacity to fund some key strategic initiatives.

2.1.7	Priority Issues in Context

The priority issues identified by the Joe Morolong Local Municipality (as exposed in paragraph 2.1.1) are based on the Council and community’s assessment of the moist pressing challenges and demands facing the Municipality. The approach followed with the compilation of this draft IDP was based on an analysis of these issues, aligned with an analysis of the institutional capacity of the Municipality to address the major challenging facing it. In this regard an attempt was made by the Municipality to match its performance targets with its institutional and resource capacity.

The issues identified as priority, and the most pressing, are a reflection of the unique nature of the Municipality, and the challenges facing it.  In this regard, the following could be specifically noted:

- The rural nature of the Municipality, characterised by vast distances and a lack of resources to adequately sponsor public transportation infrastructure.

- The need to prioritise the most fundamental and pressing needs of the community that are faced with major survival challenges, including access to clean, potable water within reasonable distances from homes, acceptable standards of sanitation facilities, and shelter.

- The need to promote the interest of special interest groups, such as women, the youth and persons with disabilities.

- The need to fast-track the growth of the local economy, and, simultaneously, create employment opportunities.

- The need to transform the Municipal Administration into an efficient vehicle for delivery.

The resource constraints that the Municipality faces in responding to these challenges could be traced back to the R72,127,000.00 that it received in the form of the equitable share and a variety of grants to be utilised for service delivery. This amounts include R98,358,268.00 allocated to fund operational expenditure, and R56,479,000.00 to fund capital projects.

3.1	The Municipal Strategy Framework

From a planning perspective, the IDP Review of the Joe Morolong Local Municipality has been drive by the following underlying principles:

- To ensure strategy alignment within the holistic national, provincial, district and local planning framework; including: Alignment with National Government’

- THE MUNICIPAL STRATEGY FRAMEWORK

- National Spatial Development Perspective, the Comprehensive Rural Development Programme, and the National Government’s prescribed legislative and planning framework for strategic and performance planning by municipalities;

- Targeted Government’s interventions, with specific reference to the Extended Public Works Programme.

- Alignment with the Northern Cape Growth and Development Strategy; and

- The growth and development priorities of the John Taolo Gaetsewe district.

- Structure the IDP (municipal strategy) in such a manner that its serves as the ultimate performance management reference document for the Municipality; meaning that the municipal objectives and strategies in the IDP must inform the performance indicators and targets of both the Municipal scorecard, as well as that of individual scorecards for section 57 managers in the Municipality.

- To formulate developmental objectives and strategies that reflects the unique challenges of the Joe Morolong Local Municipality.

3.1.1	Strategy Alignment

- National Spatial Development Perspective (NSDP)

The National Spatial Development Perspective (NSDP) has identified six categories of development potential, which are:

- Innovation and experimentation.

- High-value differentiated goods.

- Labour-intensive mass-produced goods.

- Public service and administration.

- Tourism.

- Services and retail.

If applied to the Joe Morolong Local Municipality, based on an analysis of the unique realities of the area, as exposed in Chapter 2, the positioning of Joe Morolong Municipality in terms of the identified categories could be presented as follows:

Table: Analyse strategy formulation at the Joe Morolong Municipality based on the NSDP categorisation

| Category of development potential (NSDP) | Resource Requirements | Applicable for strategy formulation in the Joe Morolong Municipality |
| --- | --- | --- |
| Innovation and experimentation | - Typically located in metropolitan or secondary urban areas. - Highly skilled labour. - Good communication networks. - High-quality living environments. | Not applicable. The Joe Morolong municipal area lacks the requirements to apply this category as a strategy formulation tool. |
| High-value differentiated goods | - Focus on local and/or global niche markets such as manufacturing and some – - Specialised agricultural or natural resource-based products. - Labour intensive mass-production. - Skilled labour. | Not applicable. The Joe Morolong municipality does not have the sophisticated labour market and resource base to utilise the category as a guide for strategy formulation. |
| Labour-intensive mass-produced goods | - Typical industries in this category include iron and steel producers. - Require high proximity to cheap transport and huge volumes of natural resources. | Not applicable. The Joe Morolong municipality does not have the required transport infrastructure, or resource base to utilise the category as a tool for strategy formulation. |
| Public service and administration | - Production processes, consumption and circulation need to be organised and controlled through business and public management. - Typically takes place in metropolitan areas, and towns and cities that perform a regional or provincial administrative function. | Not applicable, because the Joe Morolong Municipality is a purely localised authority. However, from a micro perspective the Municipality is an important vehicle for employment creation and development. |
| Tourism | - Centres on tourist attractions, such as ego-scenery, cultural heritage. - Good transport routes, safety and high quality restaurants and hotels are requirements. | Partially applicable. The Joe Morolong Municipality’s potential for tourism could be further explored in its strategies. |
| Services and retail | - Semi-skilled labour. - Presence of enterprise and people willing and able to pay are requirements. - Mostly a urban basis. | Partial applicable. However, the rural nature, high degree of unemployment and poverty (inability to pay) remains a challenge. Strategy formulation in the Municipality cannot be largely based on the category. |

It is clear from the above-mentioned analysis that the Joe Morolong Local Municipality has limited options to apply as strategy instruments for improving its economy and, with it, its social conditions, and will therefore remain dependent on government assistance to fulfil its social obligations towards the local community.

- COMPREHENSIVE  RURAL DEVELOPMENT PROGRAMME(CRDP)

“The South African Government, in consultation with a wide range of key stakeholders, launched a new stage of concerted effort to improve opportunities and well being for the rural poor.  The resulting “Comprehensive Rural Development Programme” (CRDP) was designed to realize a vision that will ‘attain socially cohesive and stable rural communities with viable institutions, sustainable economies and universal access to social amenities, able to attract and retain skilled and knowledgeable people, who are equipped to contribute to growth and development.’

The programme in its totality presents an opportunity for South Africa’s rural people to realize their own potential and contribute more fully to their country’s future. The reform of municipal government places local government in a central role in integrating programmes to achieve synergistic rural development.  Many will need assistance and guidance to develop capacity, but their role and responsibility are clearly established. Each of the line departments will make a critical contribution, and their efforts to achieve synergy and higher effectiveness in their own programmes will be assisted by the strengthened integrative mechanism at the local (municipal) provincial and national spheres.

Its initial focus was on a manageable number of selected areas, or nodes, where the process at a local level is guided. The John Taolo District Municipality preferably Joe Morolong Local Municipality because of its rural nature has been identified by the President as one of the nodes. The chief instrument for integration is the mechanisms of IDPs as provided for in the Municipal Systems Act.  Municipal councils use the IDP process to attract desired programmes from government and other sources.

The strength of the programme lied in its emphasis on a mechanism that can achieve results on the ground.  That mechanism, in brief, empowers rural stakeholders to use the IDP process to select programmes that address their priorities.  The basket of selected programmes is financed at the municipal level through an expenditure envelope comprised of the municipal budget, the commitments of the line departments through the IDP process, commitments of donor organizations and NGOs, and public-private partnerships.  Although these resources were available in the past, they lacked the integrative mechanisms described in the programme.

Although the whole District was identified as a rural node, special attention was given to Joe Morolong Municipality during the programme.

From this summery it is clear that Joe Morolong Municipality will benefit to a large extend from the programme

GANTT  CHART OF THE CRDP

| WBS | TASK NAME | Project output | ward | Locations | Responsible agency | Sources of finance | Total costs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Preparing for the process | Roles and responsibilities have to be clarified in advance and internal human resources have to be allocated accordingly.Organisational arrangements have to be established and decisions on the membership of teams , committees or forums have to be made |  |  |  |  |  |
| A1 |  |  |  |  |  |  |  |
| A2 | Laounch of CRDP |  |  |  |  |  | 00 |
| A2.2 | Establish structures |  |  |  |  |  | 00 |
| A2.3 | Workshop process & agree on roles & responsibilities. |  |  |  | JMLM |  | 00 |
| A2.4 | Agree on structures to manage development programme |  |  |  |  |  | 00 |
| A3 | Social compact/agreement |  |  |  |  |  | 00 |
| A3.1 | Prepare draft social compact |  |  |  | JMLM |  | 00 |
| A3.2 | Social compact approval by all roleplayers |  |  |  | JMLM |  | 00 |
| A3.3 | Signing of social compact/agreement. |  |  |  | JMLM |  | 00 |
| B | Analysis |  |  |  |  |  | 00 |
| B1 | PRA workshops toidentify community needs | Reconciled results from existing information and participatory analysis |  |  |  |  | 00 |
| B2 | Municipality level analysis |  |  |  |  |  | 00 |
| B3 | Priorities of tribal Authorities |  |  |  |  |  | 00 |
| B4 | Priorities of line departments |  |  |  |  |  | 00 |
| B5 | Consolidate Development priorities |  |  |  |  |  | 00 |
| B6 | Priority issues identified |  |  |  |  |  | 00 |
| B7 | Economic Analysis | Basic economic data(employment,major economic sector).Major economic trentds(growth, decline by sector)Major economic potentials (under utilized resources)Major constraints for economic development |  | Ward 1,2 & 3 of JMLM |  |  | 00 |
| B8 | Spatial Analysis and the Spatial Representation Of Development issues | Mapping the spatial dimensions of developments issues identified.Mapping major spatial patterns,trends(such as migration patterns, problems and opportunities.Mapping of spatial restructuring issues in compliance with DFA and NEMA principles. Identification and Mapping of land reform issues with respect to redistribution,restitution and tenure reform.Maps should be used as a tool during all steps of analysis . |  | Ward 1,2 and 3 of JMLM |  |  | 00 |
| C5 | Draft commerce framework | A concise (3/5 pages) document that provides a framework for any commerce promotion measures(direct or indirect) by the municipality .The localized guidelines result from an application general commerce promotion strategies to the specific local conditions | 1,2,3 |  |  |  | 00 |
| C6 | Draft Tourism Framework | A concise (3/5 pages) document that provides a framework for any commerce promotion measures(direct or indirect) by the municipality .The localized guidelines result from an application general commerce promotion strategies to the specific local conditions | 1,2&3 |  |  |  | 00 |
| C7 | Housing Framework | A concise (3/5 pages) document that provides a framework for any commerce promotion measures(direct or indirect) by the municipality .The localized guidelines result from an application general commerce promotion strategies to the specific local conditions | 1,2& 3 |  |  |  | 00 |
| C8 | Food Garden | A concise (3/5 pages) document that provides a framework for any commerce promotion measures(direct or indirect) by the municipality .The localized guidelines result from an application general commerce promotion strategies to the specific local conditions | 1,2& 3 |  |  |  | 00 |
| C9 | Social infrastructure & settlement | A concise (3/5 pages) document that provides a framework for any commerce promotion measures(direct or indirect) by the municipality .The localized guidelines result from an application general commerce promotion strategies to the specific local conditions | 1,2 & 3 |  |  |  | 00 |
| C10 | Institutional Framework | A concise document (3/5 pages) that includes , a problem statement related to the existing forms and management of service delivery | 1,2 &3 |  |  |  | 00 |
| c.11 | Locally adjusted municipal development strategies | Locally adjusted municipal development strategies |  |  |  |  | 00 |
| C12 |  |  |  |  |  |  | 00 |
| D | PROJECT-Projects proposals | Indicate for each objective.Output for each project with targets and locations.Major activities with time frame and responsible agencies .Cost estimates and budgets with sources of finance |  |  |  |  | R3,617,537,97 |
| D1 | Bulk water supply |  |  |  |  |  | R3,617,537,97 |
| D1.1. | Bulk Water Feasibility Study |  |  |  |  | DBSA,DWA Feasibility | R3,617,537,97 |
| D2 | Water reticulation |  |  |  |  |  | 00 |
| D2.1 | Madibeng(including source development) |  |  |  | JMLM |  | 00 |
| D2.2 | Eifel |  |  |  | JMLM |  | 00 |
| D2.3 | Klein Eifel |  |  |  | JMLM |  | 00 |
| D2.4 | Sesipi |  |  |  | JMLM |  | 00 |
| OS.S | Perth |  |  |  | JMLM |  | 00 |
| D2.6 | Kome |  |  |  | JMLM |  | 00 |
| D2.7 | Tsilwane |  |  |  | JMLM |  | 00 |
| D2.8 | Shalaneng |  |  |  | JMLM |  | 00 |
| D2.9 | Heuningvlei |  |  |  | JMLM |  | 00 |
| D2.10 | Makhubung |  |  |  | JMLM |  | 00 |
| D3 | Stock farmer Development |  |  |  |  |  | 00 |
| D4 | Stock farming infrastructure |  |  |  |  |  | 00 |
| D5 | Upgrading of connector roads |  |  |  |  |  | 00 |
| D6 | Access roads to farming units |  |  |  |  |  | 00 |
| D7 | Regional electricity supply |  |  |  |  |  | 00 |
| E | Integration |  |  |  |  |  | 00 |
| E1 | Develop Integrated Business Plan |  |  |  |  |  | 00 |
| E2 | Funding Plan |  |  |  |  |  | 00 |
| E3 | Stakeholder Facilitation |  |  |  |  |  | 00 |
| E3.1 | Steering committee meetings |  |  |  |  |  | 00 |
| E3.2 | WorkGroup meetings |  |  |  |  |  | 00 |
| E4 | Programme administration |  |  |  |  |  | 00 |
| E4.1 | Programme management |  |  |  |  |  | 00 |
| E4.2 | Programme management meetings |  |  |  |  |  | 00 |
| F | Implementation |  |  |  |  |  | R394,962,493.00 |
| F.10 | Link Farm access roads |  |  |  |  |  | R153,082,875,00 |
| F.10.1 | Link farm access roads Eifel to Thurso |  |  |  |  |  | 00 |
| F.10.2 | Upgrading of access roads |  |  |  |  |  | 00 |
| F.10.2.1 | Klipom |  | 2 |  |  |  | R38,270718.75 |
| F.10.2.2 | Ganap 1 & 2 |  | 2 |  |  |  | R38,270718.75 |
| F.10.2.3 | Cahar |  | 2 |  |  |  | R38,270718.75 |
| F.10.2.4 | Tlhaping |  | 2 |  |  |  | R38,270718.75 |
| F.10.4 | Enhance safety of the roads users in Joe Morolong by installing road signs |  |  |  |  |  | 00 |
| F.10.5 | Road management system |  |  |  |  |  | 00 |
| F.1 | Bulk water |  |  |  |  |  | R169,576,587.89 |
| F.1.1 | Heuningvlei bulk water supply Upgrade – Phase 1 | Construction and Refurbishment of bulk water pipeline stations,reservoirs,cattle drinking troughs and development of additional sources | 1 |  |  |  | R34,927,107.89 |
| F.1.1.1 | Resource Development |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R3,440.000.00 |
| F.1.1.2. | Full Enviromental Impact Assessment and Heritage Aplication |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R250.000.00 |
| F.1.1.3 | Design & TENDER |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R2,300,000.00 |
| F.1.1.4 | Construction Bulk |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) Agriculture | R28,403,587.89 |
| F.1.1.5. | Site Supervision Bulk infrastructure |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R533,520.00 |
| F.1.2 | Heuningvlei Bulk Water supply.Upgrade- Phase 2 | Construction and Refurbishment of bulk water pipeline stations,reservoirs,cattle drinking troughs and development of additional sources | 1 | Situated in the entire southern and western parts of ward 1 |  |  | R57,928,000.00 |
| F.1.2.1 | Resource Development |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R1,300,000.00 |
| F.1.2.2 | Full EIA and heritage application |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R450.000.00 |
| F.1.2.3 | Topographical survey |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R500,000.00 |
| F.1.2.4 | Geotechnical Report |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R100,000.00 |
| F.1.2.5 | Design & tender |  |  |  | JMLM | Bulk Infrastructure Grant (BIG) | R400,000.00 |

Although the Municipality is benefiting financially as a result of this program, it’s still enjoying the benefits in terms of technical support from provincial departments.

It is further important to note that several other projects are implemented in the municipality by provincial departments and other stakeholders.

More information on this specific programme is available from the offices of the Joe Morolong Local Municipality.

- Extended Public Works Programme (EPWP)

Though the Municipality values the President’s call on Extended Public Works Programme (EPWP).The intervention of implementing this EPWP project is to solicit adequate capacity for the management and implementation of labor based projects.Te local municipality will take advantage of their expertise long after the project has been completed. The EPWP project will be largely be constructed using labour-based techniques and therefore realize the retention of monies within the local communities.

1.LOCALITY:

Joe Morolong local Municipality is located in the Northern Cape in John Taolo Gaetsewe region.It consist of 15 wards and the geographical area covers about 9477.4560 square kilometers but with the new demarcation from 2011 it is having 15 wards. The total population of the area is about 88 236.According to STATISTICSA of 2001 the majority of the local residents live  in rural areas with  no income altogether with unemployment rate stands at 60% and the municipality is mainly rural with more than 181 villages.

EPWP PROJECT:

NAME: ERADICATION OF INVADER TREE SPECIES IN 8 JOE MOROLONG VILLAGES.

The project entails the eradication of invader species within Joe Morolong Municipality in 8 villages affected by this alien species.WARD 2: Ditlharapeng,Klipom,Cahar,Mathanthanyaneng,

Loopeng,Gamokatedi,Ganap and Laxey.The department of roads and public works commit itself to assist the municipality to promote the objectives of the EPWP.

The grant approval for the implementation of this project to a total cost of R3,092.352.00.

| NUMBER OF EMPLOYEES | TYPE OF JOBS |
| --- | --- |
| 304 JOBS | Herbicide, saw training and health and safety. |

Currently there are  30 villages in Joe Morolong affected by alien species

| CLUSTER 2 | VILLAGES |
| --- | --- |
| WARD 8 & 9 | Masilabetsane, Gamorona,Doxon 1,Doxon 2,Ditshipeng,Mmamebe, Majemantsho,Batlemount. |
| Grand Total | R3,700.000.00 |
| Number of Jobs created | 304 jobs. The project is currently in force |

FUNDING

The project is funded by the EPWP as a programme of public works  in the Northern Cape. As a result of financial constraints  from the programme the municipality only want to fund the abovementioned villages in one cluster.

CONCLUSIONS

The conclusions that can be made  are as follow:

- The alien species will be eliminated and

- Will have a positive impact of the living conditions and as well as the hygiene of the community.

- 608 short-term jobs  will be created of which 32 will be skilled jobs

- To utilise the procurement of SMME’s during  implementation.

- The project will largely be constructed using labour-based techniques and therefore realise the retaining

MAYORAL POVERTY ALLEVIATION PROJECT.

Joe Morolong is also taking heed of a call of the president of job creation through EPWP process. This kind of EPWP project is initiated by the honourable  Mayor  Esther  Molete. It is funded by Joe Morolong through the LED unit. This eradication of alien species is within 9(nine) villages. Below are projects implemented during 2011/12 financial year. Another 8 villages will be done in 2012/13 FY.

| CLUSTER 3 | VILLAGES | NUMBER OF PEOPLE EMPLOYED |
| --- | --- | --- |
| WARD 2 | GAMOKATEDI | 38 |
| WARD 2 | LOOPENG | 38 |
| WARD 4 | MAGOBING | 38 |
| WARD 5 | MAGOJANENG | 38 |
| WARD 5 | MASANKONG | 38 |
| WARD 5 | MOKALAWANOGA | 38 |
| WARD 14 | DRIELOOP | 38 |
| WARD 14 | BOJELAPOTSANE | 38 |
| WARD 14 | KGANUNG | 38 |
| 4 WARDS | NINE VILLAGES | 342 JOBS CREATED |

WATER PUMP OPERATORS PROJECT

The pump operator’s project is initiated to heed the call of job creation and effectively assist in managing of water pumps in scheme. Employment of 129 is as follow:-

- Northern Cape Growth and Development Strategy and the John Taolo Gaetsewe District Growth and Development Priorities

This document has been developed in line with the key identified issues as outline in both the Provincial Growth and Development Strategy and the District Growth and Development Strategy. These strategies are aiming at providing a framework for sustainable growth and economic development over the next ten years. They are also guided by the National Spatial Development Programme (NSDP) which seeks to achieve balanced development of economic sectors and spatial localities in accordance with the needs and potentials of the people.

The DGDS summit took place in March 2007 and the district declared its commitment towards the National and Provincial targets and objectives as contained in the vision 2014. This strategy (DGDS) also focuses on the 6 thrust considered to the main economic drive of our area. The identified focus areas are as follows:

- Agriculture

To stimulate the agricultural sector through the sustenance of commercial farming by expanding the sector through variety of value adding initiatives. Linked to this is the transformation and development of subsistence farming through capacity building, facilitating access to market, finance, infrastructure, machinery, agro-processing technology and skills.

- Infrastructure Development

Identify infrastructure backlogs to enable the district municipality to intervene decisively through the provision of infrastructure services.  The emphasis is in developing road networks that links economic activities within the District Municipality to cut the costs of doing business.  Tied to is the provision of basic service such as housing, telecommunications, water and sanitation, which are critical in jettisoning economic growth within the municipality.

- Manufacturing

Identify manufacturing opportunities from other sectors particularly mining and agriculture, linking such with the overall SMME’s strategy in the municipality.  Create export markets for regionally produced goods, both at national and international levels.

- Mining

Through understanding of the entire mining value chain with the view to identify mining opportunities like beneficiation, opening of new mines, outsourcing and procurement, share holding etc.  All these must be approached within the context of the new mining legislative framework including the Mining Charter.

- SMME Development

Set clear SMME development goals in financing and supporting SMME’s, targeting previously disadvantaged people, women, youth and people living with disabilities.  This must find practical expression in municipal institutional arrangements and all social partner’s outsourcing and procurement policies.

- Tourism

Appraise the entire district tourism sector, including operators, products and services to enable social partners to identify critical intervention areas.

3.1.2	Alignment with the Municipal Performance Management System

The strategic objectives and strategies to be formulated in this IDP would serve as the Municipality’s key performance targets for the planning period 2012-2013. It will therefore be formulated in a SMART manner to ensure that a clear performance management framework is finalised for the Municipality. The performance indicators and targets from the IDP will be cascaded down to the Municipal Service Delivery and Budget Implementation Plan and the Departmental Service Delivery and Budget Implementation Plans to align the IDP to the Municipal and Individual Performance Scorecards of the Municipality.

The intention is to ensure that a sound and effective framework is created for the review of the Municipal Performance Management System (PMS) for the 2012/13 financial year; with clear, measurable performance indicators and targets from the IDP. This will facilitate the structured, processmatic implementation of the IDP, and performance measurement in terms of the targets from the IDP.

Figure: IDP Implementation Framework

The IDP would be structured around the five Key Performance Areas prescribed in the Regulations for the Performance Management of Municipal Managers and Managers Directly Accountable to the Municipal Manager, 2006 for the performance planning and measurement of the Municipal Manager; namely:

- Municipal Transformation and Institutional Development.

- Improve Basic Service Delivery and Infrastructure Investment.

- Local Economic Development (LED)

- Financial viability and Financial Management.

- Good Governance, Communication participation and Ward Committee System.

3.1.2	Municipal Vision

: Municipal Vision and Mission

VISION STATEMENT A wealthy and prosperous local community with equal access to basic services and sustainable development opportunities.

MISSION STATEMENT We commit ourselves to develop our communities in a sustainable and democratic manner ,within the scope of affordability ; with reference to : - Participation in all decisions affecting their lives - Basic service delivery by the municipality - Socio economic development opportunities within a safe and healthy environment.

3.1.3	Municipal Performance Objectives and Projects

Being the new term of IDP for this Municipality, it is still very important for the Council to continue identifying the needs of its residents and the trends pertaining to facts and figures. It therefore embarked on an intensive participation process whereby individual ward councillors and ward committees met in order to prioritise needs or issues received from each ward.  It also investigated the basic facts and figures of the Municipality, of which the results are available in the Existing Information and Municipal Level Analysis document.  Results from these two processes were compared, leading to the identification of 10 priority issues for Joe Morolong Local Municipality for the period 2012 to 2013.  Each of these 10 issues was then analysed, setting the foundation for the development of strategies. Since the initial IDP has been reviewed annually, projects have been changed in terms of how they were prioritised, e.g. priority number one in the first IDP is no more number in the current IDP.

BASIC SERVICE DELIVERY AND INFRASTRUCTURE INVESTMENT

| Key Performance Area | Issue | Strategic (IDP) Objective | Strategies | Projects |
| --- | --- | --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Water and Sanitation | By the end of 2014, all households in Joe Morolong will have access to good quality drinking water supply systems, according to RDP standards, as well as a reduction in the sanitation backlog by 1000 on-site units per annum. | STRATEGY A: (Accessible water) Ensure a distribution of taps, 200m walking distance from each household in each village, providing at least 25 litres water per day per person. | PROJECT 1.2 Provision of water, MIG, ACIP and SLPs To provide Joe Morolong villages with water, according to RDP standards. - Garapoana (continuation) - Mokalawanoga (continuation) - Gatswinyane (continuation) - Kortnight (continuation) - Kokonye or Niks - Part of Tlapeng - Bendel |
| PROVISION OF WATER | WATER | Bulk water supply | Supply of bulk water services | - Heuningvlei bulk water supply scheme - Vanzylsrus bulk water supply - Kganoane, Cassel and Glenred Water Source Exploration and Bulk Water Supply feasibility study. - Drieloop and Kganung Water Scheme - Kikahela 1& 2 – Joe Morolong Community Water Supply Programme - Gakhoe and Garamotsokwana- Joe Morolong Community Water Supply Programme - Maphiniki, Saamsukkel, Gadiboe and Wyk 11 Bulk Water Supply |
|  |  |  | #### STRATEGY B: #### (Sustainable Water Source) Develop sufficient water sources at each village in terms of quality and quantity and electrifying boreholes in those areas where electricity is available. | PROJECT 1.1 Installation of Yard Connection To install yard connection in one village per ward |
|  |  |  | #### STRATEGY C: #### (Maintenance) Revise and implement a proper Water Service Development Plan by 2012/20123 | Project 1.3 Upgrading of Water Networks To upgrade water networks in affected areas |
|  |  |  | #### STRATEGY D: #### (Tariff System) Implement the existing tariff system and cost recovery system within 2012/2013. | PROJECT 1.5 Implement existing Tariff System Implement the existing tariff system and cost recovery system. |
|  |  |  | #### STRATEGY E: #### (Capacity Building) Launch an awareness campaign to educate people about the cost of service provision and the need for service payment and the effect of free basic services as well as the maintenance of services | PROJECT 1.6 Awareness Campaign on payment of services To educate people about the cost of service provision and the need for service payment and the effect of free basic services as well as the maintenance of services. |
|  |  |  |  | Project 1.7 Hygiene and After Care Awareness Campaign To educate people about the importance of Hygiene |
|  |  |  | #### STRATEGY F: #### (New and Improved Sanitation Facilities) Upgrading of existing sanitation facilities and building of new sanitation facilities in those villages below RDP standards, totaling 1000 on-site units per annum by the end of 2014. | PROJECT 1.8 Provision of sanitation To provide VIP and eradicate UDS Sanitation systems in all the wards of Joe Morolong Continuation of 2 052 units in to the new financial year (447 for new financial year) |
|  | Upgrading of existing and construction of new roads: Poor conditions of gravel roads and total lacking of access, -main-, and internal roads in most of the cases / insufficient roads system catering for vast area. Gravel patch work maintenance team plant | To surface Pietersham, Laxey, Tsineng roads, by end of 2014 and approving of a maintenance budget plan, within 2015/2016 Maintenance of internal roads | STRATEGY A: (Maintenance Plan) Establish and implement a proper and sufficient Maintenance Budget plan / programme, focusing on coordination of provincial and municipal budget for infrastructure upgrading to major internal and access roads | PROJECT 2.1 Identification of national roads To complete identified roads into surfaced road - Hotazel surfaced road - Battlemount culvert bridge - Dithakong culvert bridge - Molapotlase culvert bridge - Gamokatedi culvert bridge - Segwaneng culvert bridge - Motolwaneng culvert bridge - Gammakgatle internal road 2 Tipper trucks 1TLB 1self propelled roller 1motor grader 1 water tanker. |
|  |  |  |  | PROJECT 2.2 Upgrading of access roads - Makhubung (continuation) To upgrade all the access roads within Joe Morolong |
|  |  |  |  | PROJECT 2.3 Upgrading of internal roads to tar or pave To upgrade all the internal roads in the jurisdiction of Joe Morolong - Dearham |
|  |  |  | STRATEGY B: (Road signs) Enhance safety of the roads users in Joe Morolong by installing road signs | PROJECT 2.4 Upgrading of Road Signs and maintenance of bitumen surfaced roads in Joe Morolong - Signs where there are no signs - Laxey surfaced road - Wyk 10 surfaced road - Cassel surfaced road - Ncwelengwe surfaced road |
|  |  |  | STRATEGY C: | PROJECT 2.5 Road Management System To have a proper road management system in place, focusing on internal roads. |
|  |  |  | (Upgrading) Upgrade to tar, 100km of 300km roads Ensure the upgrading of storm water systems and regraveling of major internal and access roads within 5 years. | - Wyk 10 to Laxey - Laxey to Heuningvlei - Tsineng to Penryn, - Pietersham - N 14 to Camden via Khankhudung - Continuation of Bendel surfaced road - Continuation of Maphinick surfaced road |
|  |  |  | STRATEGY D: (Management System) Establish and implement a proper Management System, focusing on prioritization of major roads and alternative construction and maintenance methods and standards. | PROJECT 2.6 Road Maintenance for Joe Morolong To maintain & improve both gravel and surfaced roads in Joe Morolong |
|  | Upgrading of existing and provision of additional health services and facilities: Lack of sufficient and proper health facilities and insufficient access to the available health services | By the end of 2016, every individual living in Joe Morolong should have access to proper daily health facilities / services within a radius of 20km and according to RDP standards | STRATEGY A: (Upgrading) Improvement or upgrading of existing structures and the coordinating of services and bodies (staff and mobile services) | PROJECT 5.1 Implementation of PHC Package / Upgrade of clinic services Erection and upgrading of ± 20 clinics and health facilities. Implementation of Primary Health Care services as well as ensuring the functioning of clinics. |
|  |  |  |  | PROJECT 5.2 Provision of ambulance service To be able to serve some of the remote areas in Joe Morolong through ambulance services. |
|  |  |  |  | Project 5.3 Staffing and equipment of clinics To provide staff and equipments to all newly build clinics.(Department of health) |
|  |  |  | STRATEGY B: (New Services) Identification and prioritization of areas where additional mobile clinics and ambulances need to be procured in order to reach the objective. |  |
|  | HIV/AIDS: HIV/AIDS related diseases are one of the main contributors to mortality in the Joe MOROLONG area. | To encourage Voluntary Counselling & Testing to determine HIV/AIDS status amongst residents and reduce level of the epidemic. To work with relevant departments. | STRATEGY A: (Capacity building) To build a capacity for residents of Joe Morolong to deal with matter related to HIV/AIDS and to further encourage them for VCT within the jurisdictional area. | PROJECT 6.2 HIV/AIDS AWARENESS CAMPAIGN To educate the people on the causes and prevention on HIV/AIDS 6.1 Intensify HIV/AIDS Awareness campaigns, 6.2 Support to CBOs, 6.3 Alleviating Poverty as a result of HIV and AIDS 6.4 Human Rights (Ensuring that people are treated with dignity) |
|  | Recreational amenities: None or poor condition of community halls and related facilities in most of the wards. | Develop and upgrade all the recreational facilities within joe Morolong within 2012/2013 financial year. | STRATEGY A: (Suitable Sites) Identification of suitable sites that will be located centrally and accessible to all, and prioritisation of areas where new facilities are needed to be build, in order to reach the objective. | PROJECT 7.1 Building of new community halls Build 2 new community hall in areas not sufficiently serviced with community halls. - Ditshipeng, - Tsineng, - Gadiboe, - Padstow, - Maipeing, - Skerma - Danoon, - Ganghaai, - Magobing West - Heuningvlei |
|  |  |  | STRATEGY B: (Upgrading) Upgrading of existing community Halls and building of offices of ward committees to fulfil the function of community gathering facilities. | PROJECT 7.2 Upgrading of existing community halls Maintenance and upgrade of existing community halls Ntswaneng, Tsaelengwe, Bendel, Madula Ranch, Kikahela, Pynryn, Wyk 10, Loopeng |
|  |  |  |  | PROJECT 7.3 Office for ward councilors Provision offices and upgrading the existing buildings in each ward to serve as offices of the ward committees |
|  | Sports facilities in all wards(Mainly close grounds) |  | STRATEGY C: (Sports &Recreation) To develop sports and recreation facilities within the reach of the majority of the population in Joe Morolong. | PROJECT 7.4 Upgrading Regenerate existing sports fields and construct new fields |
|  |  |  |  | PROJECT 7.5 Sports facilities To develop one equipped sports facility in each ward |
|  | Cemeteries: Poor Condition of cemeteries and the lack of fencing, toilets and water on-site. | Upgrading of all cemeteries and provision of more cemeteries by the end of 2012/2013 | STRATEGY A: (Upgrading) Upgrading of existing cemeteries | PROJECT 8.1 Upgrading of cemeteries 80% of the existing cemeteries in Joe Morolong are not properly demarcated, fenced and cleaned |
|  |  |  |  | PROJECT 8.3 Registration of graves To develop one register for Joe Morolong Municipality indicating all the graves in the existing and newly developed cemeteries by 2016 |
|  |  |  | STRATEGY B: (New Services) # Develop new cemeteries, with a proper registrar according to legislation. | PROJECT 8.2 Development of new cemeteries To develop new cemeteries with toilets in 2012/2013 |
|  | RDP housing: Shortage of proper and sufficient housing for all. | 1000 low cost houses to be build by the end of 2016 which is in three phases.. 180 emergency houses | STRATEGY A: (Low cost houses) The development of 1000 low cost houses by the end of 2016. | Project 1000 low cost houses to be build by the end of 2016. 180 emergency houses to be build within Joe Morolong( where disaster occur) |
|  | ## Upgrading of existing and provision of additional schools and education facilities: Inadequate, insufficient and poor condition of existing education facilities. | By the end of 2014/2015, all children in Joe Morolong will have access to good quality pre-primary and primary education as well as to good proper secondary education | STRATEGY A: (Infrastructural development) To develop and upgrade the schools facilities (toilets, fence, Admin Block, Classrooms, Laboratory and Library) in the Joe Morolong area. | PROJECT 10.1 Renovations of schools To renovate all schools that are under bad conditions (Department of education) |
|  |  |  |  | PROJECT 10.2 Fencing of Schools To provide fencing for schools that are in need of fencing (department of education) |
|  |  |  |  | PROJECT 10.3 Erection of toilets To provide sanitation for schools in needy(Department of education) |
|  |  |  |  | PROJECT 10.4 Additional classes Building of additional schools where there is a need |
|  |  |  |  | PROJECT 10.5 Admin Block Building of admin blocks where there is a need |
|  |  |  |  | PROJECT 10.6 Laboratory & Library (L&L) Building of laboratory and libraries where there is a need(Department of education) |
|  | ## Public transport improvement: Lack of sufficient public transport system in a vast area | By the end of 2014/2015, all villages in Joe Morolong will be provided with public bus services, supplemented by taxi’s, on a daily basis. | STRATEGY A: (Improving Public Transport) # Improving the standard of transport in villages | PROJECT 11.1 To improve the standard of public transport across Joe Morolong villages (No costs estimates and budget) |
|  |  |  | STRATEGY B: (Service Providers) Negotiate with service providers to expand their services to those area not currently serviced. |  |
|  | ISSUE 12: Safety and Security | Prevention of wild veld fire | STRATEGY A: (Upgrading and Improving) Upgrade existing safety and security facilities (including procuring more vehicles); by the end of 2012/2013, as well as improving the in-service training work sessions (practical and theory). | PROJECT 12.1 Fire equipment and fire fighting - To implement an effective fire-prevention strategy to deal with run-away fire in the Joe Morolong Municipality - Working for fire program me |
|  | Safety and Security: | Crime free environment | Reduce crime levels considerably | Satellite Police Station To erect one satellite police station in all wards far from police services |
|  | Environmental issues: Poor optimisation, preservation and the sustainable utilisation of natural resources. | To reduce the impact of human activities on natural environment of Joe Morolong municipality in order to contribute to more sustainable development. | STRATEGY A: (Environmental sustainability) To instill into residents of Joe Morolong, a culture of preserving the natural products. | PROJECT 14.1 Environmental education and awareness To develop an environmental education and awareness campaigns amongst the residents on preserving and reserving the ecosystem in Joe Morolong |
|  | Electrification: Part of some villages should have an access to electricity. | To electrify all the outstanding extended villages and install high mast light during 2012/13 | STRATEGY A: (Electrification) Electrification of the identified outstanding villages and installation of high mast lights | PROJECT 1 To electrify the extensions of villages of within Joe Morolong during 2012/2013 financial year |
|  |  |  |  | PROJECT 2 Installation of high mast light in one village per ward. |
|  | Capacity building of Joe Morolong Municipality | To ensure a component, efficient and effective municipal administration during the 2012/13 financial year |  | PRJECT 1 - Annual review of the Skills Development plan for the municipality. - Finalization of a reviewed Recruitment and selection Policy - Finalization of a reviewed Labour relation policy. - Finalization of the annual review of the Employment Equity Plan - Annual review of the municipality ‘s organizational structure. - 2/5 section 57 managers must be women. |
|  |  | To work towards clean audit report by 2014 |  | PROJECT 2 - Finalise 4 risk assessments - Undertake one risk monitoring exercise per quarter. - Conduct 4 internal audits per annum Participate in the activities of the district’s Audit Committee |

LOCAL ECONOMIC DEVELOPMENT

| Key Performance Area | Issue | Strategic (IDP) Objective | Strategies | Projects |
| --- | --- | --- | --- | --- |
| Local Economic Development | LED projects: Lack of enough job opportunities and skill development to combat the high rate of unemployment. | Decrease in unemployment rate over 5 years as well as a 5% rise in the economy by the end of 2016. | STRATEGY A: To encourage our communities to establish income generating projects that better their lives | PROJECT 3.1 Establishment of LED Projects |
|  |  |  | STRATEGY B: SMME, BEE & Land Claims Support To support BEE/ SMME Development & Land Claims | PROJECT 3.2 Municipal support on BBBEE, SMME and land claims through land rights commission |
|  | Land Reform Issues related to land claims are not yet addressed | To ensure that all issues relating to land claims are well addressed | STRATEGY A: Follow – Ups on land claims in Joe Morolong | PROJECT 1 Responses to land claims reference to relevant departments. |

LED  PROJECTS

| NO | VILLAGE | PROJECT NAME | STATUS | WARD |
| --- | --- | --- | --- | --- |
| 1 | COE | COE DINOTSHE | NON-FUNCTIONAL | 1 |
| 2 | PERTH | BOPAGANANG FOOD PLOT | OPERATIONAL | 1 |
| 3 | PERTH | ITEKENG POULTRY | OPERATIONAL | 1 |
| 4 | GANAP | IPOLOKENG POULTRY | OPERATIONAL | 2 |
| 5 | GAPITIA | GAPITIA VEGETABLE | OPERATIONAL | 2 |
| 6 | LOOPENG | MOSHAWA BRICK LAYING | NON-FUNCTIONAL | 2 |
| 7 | SLOUGH | SLOUGH BRICK MAKING | OPERATIONAL | 2 |
| 8 | GAPITIA | GAPITIA POULTRY | OPERATIONAL | 2 |
| 9 | LOOPENG | DIRANG BASADI FOODPLOT COOPERATIVE | OPERATIONAL | 2 |
| 10 | LAXEY | IPOPENG POULTRY | OPERATIONAL | 3 |
| 11 | TSINENG | DIJO DI MO MBUNG | OPERATIONAL | 5 |
| 12 | MAIPEING | BOKAMOSO FOOD PLOT | OPERATIONAL | 5 |
| 13 | TSINENG | KAKUDI BRICKS | OPERATIONAL | 5 |
| 14 | BOSRA | BOITEKO SEWING | OPERATIONAL | 3 |
| 15 | GADIBOE | GADIBOE PIGGERY | OPERATIONAL | 6 |
| 16 | LOGOBATE | VEGETABLE GARDEN | OPERATIONAL | 6 |
| 17 | GALOTLHARE | BAIKOKOANYI FOOD PLOT | OPERATIONAL | 6 |
| 18 | TLAPENG | RATANANG BASADI SEWING | OPERATIONAL | 6 |
| 19 | LOGOBATE | BOKAMOSO HOMEBASED CARE | OPERATIONAL | 6 |
| 20 | METSIMANTSI | BOKAMOSO COFFEEMUG | OPERATIONAL | 6 |
| 21 | METSIMANTSI | METSIMANTSI CHICKEN | OPERATIONAL | 6 |
| 22 | NTSWANENG | TSHOLOFETSO GARDENING | OPERATIONAL | 6 |
| 23 | DITSHIPENG | BOITEKO MOSHAWENG | OPERATIONAL | 9 |
| 24 | BENDEL | IKAGENG FOODPLOT | OPERATIONAL | 8 |
| 25 | BENDEL | BOPANG POTTERY | OPERATIONAL | 8 |
| 26 | BENDEL | TLHABOLOLO BRICKS | OPERATIONAL | 8 |
| 27 | BENDEL | BENDEL DIKOKO | OPERATIONAL | 9 |
| 28 | DITSHIPENG | THUSANO FOODPLOT | OPERATIONAL | 9 |
| 29 | KGANUNG | TSHWARAGANANG FOODPLOT | OPERATIONAL | 14 |
| 30 | MAALOGANE | BOIKETLO POULTRY PROJECT | OPERATIONAL | 14 |
| 31 | LAXEY | LAXEY BAKERY | OPERATIONAL | 3 |
| 32 | LOGAGANENG | LESEDI KO PELE | OPERATIONAL | 7 |
| 33 | LOGAGANENG(EVERTON) | VEGETABLE PROJECT | OPERATIONAL | 7 |
| 34 | ELLENDALE | DIRANG POULTRY | OPERATIONAL | 7 |
| 35 | CHURCHILL | MOSHAWENG CAR WASH | OPERATIONAL | 7 |
| 36 | KGEBETLWANE | KGEBETLWANE PIG PROJECT | OPERATIONAL | 7 |
| 37 | GAMASEPA | IKANENG BRICK PROJECT | OPERATIONAL | 15 |
| 38 | BOTHETHELETSA | TSHIRELETSO HOMEBASED CARE | OPERATIONAL | 15 |
| 39 | TSAELENGWE | BOTSHELO NAMA POULTRY | OPERATIONAL | 15 |
| 40 | SKERMA | TIRISANO YOUTH CHICKEN | OPERATIONAL | 15 |
| 41 | MATLHABANELONG | KURUMAN COMMUNITY CHILD CARE CENTRE | OPERATIONAL | 15 |
| 42 | CASSEL | TSHWARAGANANG SUPPORT PROJECT | OPERATIONAL | 11 |
| 43 | CASSEL | GOBATLWANG FASION DESIGN PROJECT | OPERATIONAL | 11 |
| 44 | DITHAKONG | LESOM POULTRY | OPERATIONAL | 12 |
| 45 | DITHAKONG | MASILABELE FOOD PLOT | OPERATIONAL | 12 |
| 46 | CASSEL | LERUMO LA SETSHABA BRICKS | OPERATIONAL | 12 |
| 47 | GASEHUNELO(WYK 9) | AGANANG HANDWORK PROJECT | OPERATIONAL | 7 |
| 48 | LOOPENG | KALAGOLA HAND CRAFT | OPERATIONAL | 2 |
| 49 | BOTHITONG | MOLEMITSOGA FOOD PLOT | OPERATIONAL | 9 |
| 50 | MADIBENG | BATLHAROI AGRICULTURAL COOPERATIVE | OPERATIONAL | 3 |
| 51 | LAXEY | MOSHAWENG IEC COOPERATIVE | OPERATIONAL | 3 |
| 52 | LOOPENG | AGRICULTURAL COOPERATIVE | OPERATIONAL | 2 |
| 53 | CASSEL | ITSOSO GRANITE | OPERATIONAL | 12 |
| 54 | JOE MOROLONG | CHARCOAL MANUFACTURING | TO BE STARTED |  |
| 55 | JOE MOROLONG | MONGANA PROJECT | TO BE STARTED |  |
| 56 | JOE MOROLONG | DIPUDI PROJECTS | JOE MOROLONG |  |
| 57 | DITHAKONG | KGALAGADI IEC | NOT EXISTING | 12 |
| 58 | ELLENDALE | REKOPANE OSTRICH | NOT EXISTING |  |
| 59 | LAXEY | VEGETABLE PROJECT | EXISTING | 3 |
| 60 | LAXEY | IKAGENG BEEF PROJECT | EXISTING | 3 |
| 70 | DITHAKONG | SAND MINING | EXISTING | 12 |
| 71 | CASSEL | ITSOSO GRANITE | EXISTING | 11 |
| 72 | LAXEY | LAXEY SAND MINING | EXISTING | 3 |
| 73 | PERTH | DIPODI PROJECT | EXISTING | 1 |
| 74 | PERTH | BONTLE BO A ITIRELWA | EXISTING | 1 |
| 75 | KOME | IKETLETSO FOOD PLOT | EXISTING | 1 |
| 76 | VANZYLSRUS | TSHWARAGANANG DIPODI PROJECT | EXISTING | 4 |
| 77 | VANZYLSRUS | GOLANG WOODCRAFT | EXISTING | 4 |
| 78 | VANZYLSRUS | BOKAMOSO SEWING | EXISTING | 4 |
| 79 | VANZYLSRUS | DIKOKO PROJECT | EXISTING | 4 |
| 80 | METSIMANTSI WYK 9 | KGATELOPELE DIPODI PROJECT | EXISTING | 6 |
| 81 | DOXON 1 | THUSANO FOOD PLOT | EXISTING | 8 |

| Key Perfo mance Area | Issue | Strategic (IDP) Objective | Strategies | Projects |
| --- | --- | --- | --- | --- |
| Municipal Institutional Transformation and MUNICIPAL INSTITUTIONAL TRANSFORMATION AND DEVELOPMENT Development | Review of human resource policies | Finalisation of human resource policies | STRATEGY A: Reviewed policy be submitted to council for approval | PROJECT 4.1 accessability and implementation of human resource policies |
|  | Review of employment equity plan | Finalisation of review of employment equity plan | .Review of employment equity plan be submitted to council for approval. | PROJECT 4.2 Availability and implementation of employment equity plan |
|  | Review of skills development plan | To review and ensure implementation of skills development plan | # To review skills development plan be submitted to council for approval | PROJECT 13.1 To ensure that councillors and officials are trained in accordance with skills development plan |
|  | Review of municipal structure | To ensure annual review of municipal structure in reduction of the vacancy rate to improve municipal capacity to give practical effect to its mandate | To review municipal structure and submitted to council for approval | PROJECT 13.2 Ensure that municipal structure is reviewed |
|  | Functionality of local labour forum | Ensure that labour forum is functional | To ensure that there is schedule for meetings | Availability of schedules and and minutes. |
|  |  |  |  | PROJECT 13.3 |

GOOD GOVERNANCE AND PUBLIC PARTICIPATION

| Key Performance Area | Issue | Strategic (IDP) Objective | Strategies | Projects |
| --- | --- | --- | --- | --- |
| Good Governance and Public Participation | Special Projects: Issues affecting youth, women and disabled are not well addressed | To establish special projects addressing issues affecting youth, woman and disabled | STRATEGY A: Community consultation on reviewal of youth development strategy Review youth development strategy and take it to council for approval | PROJECT 1 Accessability and implementation of youth development strategy . |
|  | HIV and AIDS | To conduct 4 HIV and AIDS awareness campaigns during 2012/13 financial year | To encourage community members to do voluntary testing | Conduct HIV and AIDS awareness campaigns |
|  | Ward Committees | Functionality of ward committees | To encourage ward committees in public participation | To have monthly ward committee meetings |
|  | Disaster management | To effectively manage disaster and prevention there of on an urgency basis | To manage disaster issues | To attend to all disaster cases as per the capacity of the municipality |
|  | Library services | To monitor and manage libraries in Joe Morolong jurisdiction. | To popularize and ensure the usage of library services | To ensure accessability of library services |
|  | Environmental issues | To promote safe and healthy environment | To encourage communities to live in a safe | To conduct environmental awareness campaigns |
| Basic services | Road safety | Promote a safe environment | Ensure that community live in a safety environment | Registration and establishment of traffic department: Phase 1- construction of testing ground |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Water and Sanitation | By the end of 2014, all households in Joe Morolong will have access to good quality drinking water supply systems, according to RDP standards, as well as a reduction in the sanitation backlog by 1000 on-site units per annum. |

BASIC SERVICE DELIVERY AND INFRASTRUCTURE INVESTMENT

| Strategies | Projects | Location |  | Target Set | Objective |  |  | Cost Estimate | Budget |  |  | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Water | Heuningvlei bulkwater supply | Ward 1 and parts of wards 2 and 3 |  | Scheme to be in place before June 2014 | To have the second phase of the bulk scheme completed |  |  |  | R48,000,000.00 |  |  | There is a commitmentof R103.000 000.00 Towards the project indicatively showedby DORA and substanciated by the department |
|  | Bulk connection for low cost houses.. |  |  |  |  |  |  |  | R2,500,000.00 |  |  |  |
|  | Madibeng bulk water |  |  |  |  |  |  |  | R6,800,000.00 |  |  | Assmang |
|  | Maipeing Water Project(phase 2) |  |  |  |  |  |  |  | R4,900,000.00 |  |  |  |
|  | Water backlog at Dithakong |  |  |  |  |  |  |  | R6,017,000.00 |  |  |  |
|  | yard connections one village per ward. |  |  |  |  |  |  |  | R350,000.00 |  |  |  |
|  | Development and implementation of a proper WSDP |  |  |  |  |  |  |  | R2,250,000.00 |  |  |  |
|  | Water maintenance |  |  |  |  |  |  |  | R5,000,000.00 |  |  |  |
|  | Upgrading of water supply at Maphiniki,Gadiboe, Samsukkel |  |  |  |  |  |  |  | R6,500,000.00 |  |  |  |
| (Accessible water) Ensure a distribution of taps, 200m walking distance from each household in each village, providing at least 25 litres water per day per person. | 1.2 Provision of water in Joe Morolong With backlock of 1 160 households | Ward 1 Heuningvlei to Madibeng Ward 2 Garapoana Ward 5 Mokalawanoga WARD 9 Gatswinyane |  | Priority list | To ensure access to efficient, affordable, economical and sustainable water services to all consumers in the municipal area |  |  | R78,000,000 @ R3,000,000 Per project | Garapoana:R10 353 021.87 MokalawanogaR4 518 846. 99 Gatswinyane:R8 596 774.25 |  |  | Joe Morolong Municipality Mr Molusi (From MIG - DORA 3 yrs Alloc. & indicatives) MIG MIG MIG |
| #### STRATEGY B: #### (Sustainable Water Source) Develop sufficient water sources at each village in terms of quality and quantity and electrifying boreholes in those areas where electricity is available. | PROJECT 1.1 Installation of Yard Connection ,Yard connection per request | Per request |  | 250 yard connections | To provide communities with an upgraded level of services (water connections) |  |  | R6,600,000 @ R600,000 per village |  |  |  | Joe Morolong Municipality (Mr Molusi) (From equitable share- DORA 3 yrs Alloc. & indicatives) |
| #### STRATEGY C: #### (Maintenance) Develop and implement a proper Water Service Development Plan by 2011/20112. | Project 1.3 Upgrading of Water Networks To upgrade water networks in affected areas | Upgrading in villages and refurbishment in all affected villages | To refurbish and upgrade water networks in affected wards |  |  | R51,000,000 @ R1,500,000 per project |  |  |  | Mr Molusi |
|  | PROJECT 1.4 Water Maintenance Develop and implement a proper WSDP | All municipal villages |  | On – going | To develop and implement Water Maintenance Plan |  |  |  |  |  |  | JMunicipality Mr Molusi |
| #### STRATEGY D: #### (Tariff System) To implement existing tariff system and cost recovery system within 2012/2013. | PROJECT 1.5 Implement Tariff System Implement the revised tariff system and cost recovery system. | Joe Morolong Municipality |  | 2012 / 2013 | To implement the revise the existing tariff system and cost recovery system |  |  |  |  |  |  | Joe Morolong Municipality Mr Molusi |
| #### STRATEGY E: #### (Capacity Building) Launch an awareness campaign to educate people about the cost of service provision and the need for service payment and the effect of free basic services as well as the maintenance of services | PROJECT 1.6 Awareness Campaign on payment of services To educate people about the cost of service provision and the need for service payment and the effect of free basic services as well as the maintenance of services. | All villages in Joe Morolong Municipality |  | Four campaigns per ward | To educate people about the cost of service provision and the need for service payment and the effect of free basic services as well as the maintenance of services. |  |  |  |  |  |  | Joe Morolong Municipality Mr Molusi |
|  | Project 1.7 Hygiene and After Care Awareness Campaign To educate people about the importance of Hygiene | All villages in Joe Morolong Municipality |  | Four campaigns per ward | To educate people about the importance of hygiene |  |  |  |  |  |  | Joe Morolong Municipality Mrs Mabudi |
|  |  |  |  |  |  |  |  |  |  |  |  | Joe Morolong Municipality Mr Molusi (From MIG – DORA 3 yrs Alloc. & indicatives) |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Upgrading of existing and construction of new roads: Poor conditions of gravel roads and total lacking of access, -main-, and internal roads in most of the cases / insufficient roads system catering for vast area. | To surface Pietersham, Laxey, Tsineng and Bendel roads, by end of 2016 and approving of a maintenance budget plan, within 2012/2013 |

| Strategies | Projects |  | Location |  | Target Set | Objective |  | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Maintenance Plan) Establish and implement a proper and sufficient Maintenance Budget plan / programme, focusing on coordination of provincial and municipal budget for infrastructure upgrading to major internal and access roads | PROJECT 2.1 Completion of national roads To complete identified roads into sub- standard surfaced road |  | Heiso-Dithakong (D 310) Wyk10 to -Laxey (D321) |  | 2012/13 2012/13 2012/13 | To construct 2 district roads in phases |  | R13 million |  | Dep.Transport, Roads & Public Works |
|  | 50% gravel surfaced at 50% paved surface |  |  |  |  |  |
|  | PROJECT 2.3 Upgrading of internal roads To upgrade all the internal roads in the jurisdiction of Joe Morolong |  | All villages in Joe Morolong Churchill –tarred internal road |  | Two tarred or paved roads: 2.5 km each | To construct 5 km of the internal roads in two villages to tarred or paved roads |  | R3,500,000.00 |  |  |
| STRATEGY B: (Road signs) Enhance safety of the roads users in Joe Morolong by installing road signs | PROJECT 2.4 Upgrading of Road Signs in Joe Morolong To improved & provided road signs where there are none |  | All wards / villages in Joe Morolong |  | 2012/13 | To provide, maintain and increase the number of road signs |  | R5,000,000 |  |  |
| STRATEGY C: (Upgrading) Ensure the upgrading of storm water systems and regraveling of major internal and access roads | PROJECT 2.5 Road Management System |  | Joe Morolong Municipality |  | 2012/13 2012/13 | To have a proper road management system in place, focusing on internal roads. |  | R1,000,000 |  |  |
| STRATEGY D: (Management System) Establish and implement a proper Management System, focusing on prioritization of major roads and alternative construction and maintenance methods and standards. | PROJECT 2.6 Road Maintenance for Joe Morolong To maintain & improve both gravel and surfaced roads in Joe Morolong |  | Joe Morolong Municipality |  | 2012/13 | To have a proper road management system in place, focusing on internal roads. |  | R7,000,000 |  | From equitable share- DORA 3 yrs Alloc. & indicatives |
|  | Deorham, low volume traffic gravel road |  |  |  |  |  |  |  | R4,500,000.00 |  |
|  | Interlocking blocks surfaced roads at Maphiniki (internal roads) tarred. |  |  |  |  |  |  |  | R2,953,800 |  |
|  | Interlocking blocks surfaced roads at Bendel (internal road) tarred. |  |  |  |  |  |  |  | R2,508,610 |  |
| Internal roads | - Bridges - Bridges - Internal road |  | Between Tlhokomelang and Gadiboe (Legobate and Galotlhare Motolwaneng(6) Galotlhare, Gadiboe, Goodhope, Hertzog Wingate, wyk 11,wyk 1 Churchill- from cemeteries to tarred road |  |  |  |  |  |  |  |
| Internal roads |  |  |  |  |  |  |  |  |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Upgrading of existing and provision of additional health services and facilities: Lack of sufficient and proper health facilities and insufficient access to the available health services | By the end of 2016, every individual living in Joe Morolong should have access to proper daily health facilities / services within a radius of 20km and according to RDP standards |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | HIV/AIDS: HIV/AIDS related diseases are one of the main contributors to mortality in the Joe Morolong area. | To encourage Voluntary Counseling & Testing to determine HIV/AIDS status amongst residents and reduce level of the epidemic. |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Capacity building) To build a capacity for residents of Joe Morolong to deal with matter related to HIV/AIDS and to further encourage them for VCT within the jurisdictional area. | 6.1 Intensify HIV/AIDS Awareness campaigns, 6.2 Support to CBOs, 6.3 Alleviating Poverty as a result of HIV and AIDS 6.4 Human Rights (Ensuring that people are treated with dignity) | All the Wards in Joe Morolong | On – going one awareness campaigns per ward | To provide a comprehensive, accessible HIV and AIDS programme in Joe Morolong | 50,000.00 |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Recreational amenities: None or poor condition of community halls and related facilities in most of the wards. | Develop and upgrade all the recreational facilities within Joe Morolong within 2012/2013 financial year. |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Suitable Sites) Identification of suitable sites that will be located centrally and accessible to all, and prioritisation of areas where new facilities are needed to be build, in order to reach the objective. | PROJECT 7.1 Building of new community halls Build 2 new community hall in areas not sufficiently serviced with community halls. | Joe Morolong area Tsineng, Ditshipeng, Padstow, Gadiboe, Khankhudung Maalogane, Bosra, Metswatsaneng, Laxey, Genhaai, Danoon, Magobing West, Churchill | 4 new halls | To build 2 new community hall annually in areas not sufficiently serviced with community halls | R15,000,000 Averaging R1,500,000 per each |  | (from equitable share- DORA 3 yrs Alloc. & indicatives) John Taolo Development trust |
| STRATEGY B: (Upgrading) Upgrading of existing community Halls and building of offices of ward committees to fulfill the function of community gathering facilities. | PROJECT 7.2 Upgrading of existing community halls To upgrade 3 existing community halls | Ntswaneng, Penryn, Bendel | 2 halls | To renovate 2 existing community halls annually | R7,500,000 Averaging R750,000 each |  |  |
|  | PROJECT 7.3 Office for ward councilors Provision offices and upgrading the existing buildings in each ward to serve as offices of the ward councilors and committees | All wards / villages in Joe Morolong | Purchase equipments for ward councillors offices | To purchase equipments for ward councillors offices (laptops for all ward councillors) | R3,300,000 |  |  |
| STRATEGY C: (Sports &Recreation) To develop sports and recreation facilities within the reach of the majority of the population in Joe Morolong | PROJECT 7.4 Greenifying Regenerate existing Laxey sports fields and construct new field in Dithakong to suit sports activities | All wards / villages in Joe Morolong Penryn, Loopeng, Bendel. | Construction of 2 new sports field and upgrading of 7 | To regenerate existing sports field and construct new sports field in areas not sufficiently serviced with greenified sports fields | R27,500,000 averaging R2,500,000 per ward |  |  |
|  | PROJECT 7.5 Sports facilities To develop one equipped sports facility in each ward | Penryn, Loopeng, Bendel, Metswatsaneng, Cassel, Dithakong. |  |  |  |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Cemeteries: Poor Condition of cemeteries and the lack of fencing, toilets and water on-site. | Upgrading of all cemeteries and provision of more cemeteries by the end of 2012/2013 |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Upgrading) Upgrading of existing cemeteries | PROJECT 8.1 Upgrading of cemeteries 50% of the existing cemeteries in Joe Morolong are properly demarcated, fenced and cleaned New piloted cemetery project(from National) | All wards / villages in Joe Morolong MTEF Ward 1 Heuningvlie Madibeng Ward 2 Mathanthanyaneng Loopeng Ward 5 Maipeing Gasese Ward 6 Wyk 8 Motolwaneng CHURCHILL |
| STRATEGY B: # Develop new cemeteries, with a proper registrar according to legislation. | PROJECT 8.2 Development of new cemeteries To develop new cemeteries in 2012/2013 | All wards / villages in Joe Morolong |  | To upgrade existing cemeteries with quality services (access roads, water and sanitation) |  |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | RDP housing: Shortage of proper and sufficient housing for all. | 1000 low cost houses to be build by the end of 2012/2013. |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Low cost houses) The development of 1000 low cost houses by the end of 2012/2013. houses in Joe Morolong | Project 9 1000 low cost houses to be build by the end of 2012/2013. | All wards / villages in Joe Morolong MTEF Ward 3 Madibeng Eithel Klein Eifell Ward 2 Padstow Ward 5 Danoon | 600 units | To ensure that there is proper and sufficient housing for all | R176,000,000 | R12,000.000.00 FOR 2012/13 | Dep. Housing & Local Government |

| Key Performance Area | Issue | Strategic (IDP) Objective |  |
| --- | --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | By the end of 2016, all children in Joe Morolong will have access to good quality pre-primary and primary education as well as to good proper secondary education |  |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Infrastructural development) To develop and upgrade the schools facilities (toilets, fence, Admin Block, Classrooms, Laboratory and Library) in the Joe Morolong area. | PROJECT 10.1 Renovations of schools To renovate all schools that are under bad conditions | Tongwane Intermediate School,March Primary school, Khuis primary school,Resolofetse Intermediate school Magonono Middle School. All High Schools in Joe Morolong. |  |  |  |  |  |
|  | PROJECT 10.2 Fencing of Schools To provide fencing for schools that are in need of fencing | All schools in Joe Morolong without fence |  |  |  |  |  |
|  | PROJECT 10.3 Erection of toilets To provide sanitation for schools in needy |  |  |  |  |  |  |
|  | PROJECT 10.4 Additional classes Building of additional schools where there is a need | All the villages All the wards |  |  |  |  |  |
|  | PROJECT 10.5 Admin Block Building of admin blocks where there is a need |  |  |  |  |  |  |
|  | PROJECT 10.6 Laboratory & Library (L&L) Building of laboratory and libraries where there is a need | (LIBRARY) Churchill Extended to all the villages |  |  |  |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | ## Public transport improvement: Lack of sufficient public transport system in a vast area | By the end of 2014, all villages in Joe Morolong will be provided with public bus services, supplemented by taxi’s, on a daily basis. |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Improving Public Transport) # Improving the standard of transport in villages | PROJECT 11.1 To improve the standard of public transport across Joe Morolong villages (No costs estimates and budget) | To improve the standard of public transport across Joe Morolong villages |  |  | (No costs estimates and budget) | (No costs estimates and budget) |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |  |
| --- | --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Reduce the high crime rate by the end of 2012/2013. |  |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Upgrading and Improving) Upgrade existing safety and security facilities by the end of 2012/2013, as well as improving the in-service training work sessions (practical and theory). | PROJECT 12.1 Fire equipment and fire fighting To implement an effective fire-prevention strategy to deal with run-away fire in the Joe Morolong Municipality | Churchill in Joe Morolong municipality | Equipped satellite disaster management centre | Establish an Equipped satellite disaster management centre |  |  |  |
|  | PROJECT 12.2 Satellite Police Station To erect one satellite police station in all wards far from police services | All wards except ward 5, 3 & 10 | 2012/ 2013 | Erect one Satellite police station in all affected wards |  |  |  |
| STRATEGY B. (Disaster management) To effectively manage disaster and the prevention thereof on an agency basis. |  |  |  |  |  |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Environmental issues: Poor optimisation, preservation and the sustainable utilisation of natural resources. | To reduce the impact of human activities on natural environment of Joe Morolong municipality in order to contribute to more sustainable development. |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Environmental sustainability) To instill into residents of Joe Morolong, a culture of preserving the natural products. | PROJECT 14.1 Environmental education and awareness To develop an environmental education and awareness campaigns amongst the residents on preserving and reserving the ecosystem in Joe Morolong | Environmental education and awareness | All wards / villages in Joe Morolong | 2012/13 | Increase awareness amongst communities concerning sensitive environmental areas |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Improve Basic Service Delivery and Infrastructure Investment | Electrification: Part of some villages should have an access to electricity. | - To electrify the following village extensions by 2012/13 - Dithakong Extension - Lotlhakajaneng - Lykso Washington 22kv new Hare Line - Lykso sub-installation of 10 MVA - Van Zyl’s Rus - Electrify other villages extensions on the outer years - and install high mast light - Upgrade of the Heuningvlei Substation |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: (Electrification) Electrification of the identified outstanding villages and installation of high mast lights | PROJECT 1 To electrify all the extended villages within Joe Morolong during 2012/2013 financial year | All the extentions and infils | 2012 / 2013 | To electrify all the outstanding extended villages and in fills |  |  |  |
|  | PROJECT 2 Installation of high mast light in one village per ward. Installation of high mast lights in 1villages per ward annually. | All the wards without high mast light | One village per ward 2012/13 financial year | To install high mast lights in villages | R28,437.000 |  | MIG-DORA 3 yrs alloc. & indicative |

LOCAL ECONOMIC DEVELOPMENT

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Local Economic Development | LED projects: Lack of enough job opportunities and skill development to combat the high rate of unemployment. | Decrease in unemployment rate over 5 years as well as a 5% rise in the economy by the end of 2016. |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: To encourage our communities to establish income generating projects that better their lives | PROJECT 3.1 Establishment of LED Projects | ALL WARDS | 2012/13 | Poverty alleviation |  | R4,000,000.00 |  |
| STRATEGY B: SMME, BEE To support BEE/ SMME . | PROJECT 3.2 Municipal support on BBBEE, SMME | ALL WARDS | 2012/13 | SMME Support |  | R500,000.00 |  |
|  | Kiang kop cultural village | Kiangkop | 2012/13 | Heritage site |  | R3,500,000,000 | ASSMANG SLP |
|  | Community participation | All wards | 2012/13 | IDP roadshows |  | R250,000.00 |  |
|  | two vehicles for LED unit | churchill |  |  |  | R250,000.00 |  |

COMMUNITY SERVICE

| STRATEGY | Projects | location | Target set | Objective | Cost estimate | budget | funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Land fill site | Glenred | 2012/13 |  |  | R3,500,00 |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Local Economic Development | Land Reform Issues related to land claims are not yet addressed | To ensure that all issues relating to land claims are well addressed |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: Follow – Ups on land claims in Joe Morolong | PROJECT 1 Responses to land claims ) | All affected areas | 2012 / 2013 | To ensure that all issues relating to land redistribution and restitution are well addressed |  |  | Land Affairs |

MUNICIPAL INSTITUTIONAL TRANSFORMATION AND DEVELOPMENT

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Municipal Institutional Transformation and Development | Capacity building of Joe Morolong Municipality: Improper financial and administration management in Joe Morolong Municipality, due to the lack of capacity. (Councillors and officials) | By the end of 2016, Joe Morolong Municipality will be a financially & administratively established municipality. |

| Strategies |  | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY B: (Appointment of staff) ##### The appointment of staff members in crucial positions, that is human resource and finance |  | PROJECT 4.2 Capacity building of Joe Morolong Municipality Joe Morolong Municipality will be equipped with properly skilled staff operating according to the budget | Joe Morolong area | 2012/13 | To establish a broad band Communication facility and a fully functional IT network and Telecommunication network |  |  |  |

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |

GOOD GOVERNANCE AND PUBLIC PARTICIPATION

| Key Performance Area | Issue | Strategic (IDP) Objective |
| --- | --- | --- |
| Good Governance and Public Participation | Special Projects: Issues affecting youth, women and disabled are not well addressed | To establish special projects addressing issues affecting youth, woman and disabled |

| Strategies | Projects | Location | Target Set | Objective | Cost Estimate | Budget | Funder |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STRATEGY A: Establishment of special projects office | PROJECT 1 Special projects officers | Municipal offices | 16.1 Youth development Programme/council 16.2 Children’s Programme | Municipal offices |  |  |  |

IDP PROJECT ALIGNED TO THE BUDGET FOR 2012/ 2013 FINANCIAL YEAR

| PRIORITIES FOR 2011/ 2012 (KPA) | PROJECTS FOR 2011/ 2012 | COMPLETE/INCOMPLETE 2011/ 2012 | WARD | PROJECTS FOR 2012/ 2013 |
| --- | --- | --- | --- | --- |
| 1. Provision of water. 1.1.Provision of basic water | Heuningvlei bulk water supply = R35,000.00 subject to verification with DWA. | Continue to 2012/13. . | 1 ,2 and part of 3 | Second phase of Heuningvlei bulk water supply R48,500,000.00 |
|  | Garapoana | Projected to 201/13 | 2 | Garapoana Water Scheme Ward 2= R10,359,273.00 |
|  | Gatswinyane | Projected to 2012/13 FY |  | Gatswinyane R8,000,000.00 |
|  | Mokalawanoga | Projected to2012/13 | 5 | Mokalawanoga Ward 3 R4,521,487.77 |
|  | Eradication of water backlog in three villages: Tlapeng.(ACIP) | Projected to 2012/13 | 6 | Eradication of water backlog in Tlapeng.(ACIP R2,641,000.00 |
|  | Access to basic water in Ditlharapaneng | Projected to 2012/13 | 5,2 | Access to basic water in Ditlharapeng (ASSMANG SLP) R4,742,425.00 |
|  | Madibeng Water Reticulation | Projected to 2012/13 | 3 | CRDP (ASSMANG SLP) R7,980,521 |
|  | EiffelWater Reticulation | Projected to 2012/13 | 3 | CRDP (ASSMANG SLP) R2,743,870 |
|  | Eradication of Water shortage in Van Zylsrus |  | 4 | R2,700,000.00 (ACIP + Own Funding) |
|  | Eradication of Water shortage in Klein Naira |  | 7 | Eradication of Water shortage in Klein Naira R2,850,000.00 |
|  | Eradication of water backlog in Bendel |  | 8 | Eradication of water backlog in Bendel R5,516,000.00 |
|  |  |  |  | Water supply Scheme in Kokonye or Niks R5 118 845.00 |
| Yard connections | Yard connections to all villages in Joe Morolong | 100 households in Cassel | all | It is done per request(application) |
| Engine repairs in all wards | Replacement of leaking 10kl tanks,replacement of diesel engines and fencing of pump houses |  | ALL | R4,540,000.00 |
| Upgrading of water networks |  | R1 090 705.00 | 3 | Upgrading of water networks in Klein Eiffel (ASSMANG SLP) R1 090 705.00 |
| Upgrading of water networks |  | R2 743 870.00 | 3 | Upgrading of water networks in Eiffel (ASSMANG SLP) R2 743 870.00 |
| Revised tariff system | Revise the existing tariff system and cost recovery. |  | all |  |
| 2.2. Awareness campaign on payments of services | To have campaigns on educating people about the cost of service provision ,the need for service payment and the effect of basic services and as well as the maintenance of services. |  | all | In all IDP roadshows |
| 3. Hygiene and aftercare Awareness campaign | To have campaign educating people about the importance of health and Hygiene. |  | all | In all IDP roadshows. |
| 4.1 HIV/AIDS | To conduct 4 HIV and AIDS campaign. |  |  | To conduct 4 HIV/AIDS campaign in collaboraton with other sector departments |
| 4.2 Youth | All matters affecting youth to be refered to youth office at the Municipality |  | all | e.g bursaries and Unemployment |
| World aids day | To commemorate World HIV and AIDS day |  |  | 1 December 2012 |
| Activism against women and children |  |  |  | 25 November to 5 December 2012 |
| Sanitation |  |  |  | To be completed in 2012/13 FY |
|  | Metsotswaneng | Continuation | 14 | To be completed in 2012/13 |
|  | Ntswelengwe | Continuation | 15 | To be completed in 2012/13 |
|  | Glen Red | Continuation | 10 | To be completed in 2012/13 |
|  | Camden | New Project | 13 | R4 474 188. 00 |
| Roads |  |  |  |  |
| To complete identified roads into sub standards surfaced road: | Tsineng-Hotazel road Phase 1 and 2 (BHP Billiton and the Department of Roads and Public works) | continuation | 4 ,5 | The road will be stretched from Severn road through the villages of Magobing,Magojaneng and it will join the road from Batlharos to tsineng |
| Upgrading of access roads | Kamden –Kikahela Vanzylsrus-Askham |  |  | Regravelling by Dept. of Roads and Public Works |
|  | Planning of Construction of Road from N14 via Khankhudung to Camden | New Projects | 13 | N14 via Khankhudung to Camden R3 928 296.00 (KUMBA) |
| 6.3. Internal Roads To upgrade internal roads into tarred or paved roads, 2.5 km each. | Construction of Bendel Phase 2 | Continuation | 8 | Construction of Bendel Phase 2 R 3 102 125.00 |
|  | Construction of Maphinick Phase 2 | Continuation | 6 | Construction of Maphinick Phase 2 R 2 969 577.00 |
|  | Construction of Deurham | New Project | 8 | Construction of Deurham R5 750 000.00(ASSMANG) |
|  | Construction of Makhubung | New Project | 1 | Construction of Makhubung R5 965 584.00 |
| Upgrading of Cemeteries | Heuningvlei Madibeng | incomplete | 1 3 | To be projected to 2012/13 |
|  | Mathanthanyaneng Garapoana |  | 2 |  |
|  | Maipeing Gasese |  | 5 |  |
|  | Permonkie Motolwaneng Wyk 8 |  | 6 |  |
|  | Gatswinyane Ditlharapeng |  | 8 |  |
|  | Wyk 4, 10 & Wyk 6 |  | 7 |  |
|  | Kgebetlwane Radiatsongwa |  | 7 |  |
|  | Washington Bothetheletsa |  | 14 |  |
|  | Dithakong |  | 12 |  |
|  | Glenred Gamakgatle Diwatshane |  | 10 |  |
|  | Gammatlhoro, Gamatolong |  | 13 |  |
|  |  |  | 15 | To be identified |
| Development of one register for Joe Morolong(cemeteries) |  | New Projects | ALL |  |
| Land fill sites | Glenred land fill site |  | 10 | R3,500,000.00 |
| Electricity To electrify all extended villages in Joe Morolong. | Dithakong ext. Lotlhakajaneng Lykso, Washington (LWA)22kV new Hare line Lykso sub-installation of 10MVA-trf and fdr lay Vanzylsrus | New Projects New Project | 12 | R684,000.00(40 connections) R1,313,000.00(72 connections) R721,050.00 R8,670,365.00 R4,121,100.00(241 connections) |
| Community facilities | New Community Halls in Khankhudung & Gadiboe | Continuation | 6 & 13 | New Community Halls in Khankhudung & Gadiboe |
|  | New community Halls in Danoon,Tsineng and Heuningvlei | New Projects | 1,5 | (JTG Development Trust) |
|  | Upgrading of Vanzylsrus Multipurpose Centre | New project | 4 | (Dept.of Roads and Public Works) |
| HOME BASED CARE CENTRES | Dithakong,Esperanza,Kanana,Cassel and Botheteletsa | New Projects | 12,7,11 | (JTG Development Trust) |
| LIBRARIES AND SCIENCE LABS | Bendel,Cassel,Dithakong,Madularanch | New projects | 8,12,10,11 | (JTG Development Trust) |
| ECD’S | Churchill,Maphiniki,Segwaneng | New Projects | 6,7 | (JTG Development Trust) |
|  | ECD classroom at Glenred Primary School | New Project | 10 | R3 481 794.09((KUMBA) R466 666.66 For equipments(KUMBA) |
|  | ECD Classroom at Cassel :Simololang Primary | New project | 11 | R3 481 794 .09(KUMBA) R466 666.66 For equipments(KUMBA) |
|  | ECD Classrooms at Dithakong | New project | 12 | R3 481 794 .09(Dept of Education) R466 666.66 For equipments(KUMBA) |
| HALLS | Two new Community Halls | New Projects |  | To be Identified |
| EDUCATION | Dibotswa H.S. extension | New project |  | R2,000,000.00(ASSMANG SLP) |
|  | Bursary Scheme | New Project |  | R1,000,000.00(ASSMANG SLP) 30 STUDENTS |
|  | Schools Motivational talks Teacher Development training | New Project |  | R500,000.00(ASSMANG SLP) R500,000.00(ASSMANG) |
|  | career exhibition2012 | New project |  | R500,000.00(assmang) |
| LED | Laxey Sand Mine Support | New Project | 3 | R1,837,346.00(ASSMANG) |
|  | Dithakong Sand Mining | New Project | 12 | R4,000,000.00(assmang SLP) |
|  | Kiangkop Tourism Development (phase 3) | New Project |  | R3,398,111.00(ASSMANG SLP) |
|  | Foodplot initiative(Tsineng and Ntswaneng) | New Project | 5,6 | R1,410,000.00(ASSMANG) |
|  | SMME mentoring and coaching SMME Capacity building and training | New Project |  | R2,000,000.00(ASSMANG) R1,000,000.00(ASSMANG) |
| Municipal annual IDP planning | Implementation of IDP Process Plan | Ongoing process | all | R250,000.00 |
| SPORTS FIELD | Erection of one sports field | New Project |  | Areas to be Identified |
| HOUSING | 180 DISASTER HOUSES IDENTIFIED(to be implemented in 53 villages) | New Project | All | To be build in 2012/13 FY R12,279,859.20(COGHSTA) |
|  | 2 houses approved under Mandela Day Programme(Deorham and Damros) | New Project |  | R130,000.00(COGHSTA) |
| RDP HOUSES | 100 new Allocation (56 Padstow,44 Heuningvlei) | Continuation | 1 & 2 | R6 785 400.00 (COGHSTA) |

SECTOR DEPARTMENTS  PROGRAMMMES

EDUCATION

| ECD |  | Tselancho Primary School:1 single classroom |  | R500, 000.00 | Budgeted for 2012/2013 |
| --- | --- | --- | --- | --- | --- |
|  |  | Lerumo Primary School: 1 single classroom |  | R500, 000.00 | Budgeted for 2012/2013 |
|  |  |  |  |  | 2013/2014 |
| ABLUTION BLOCK |  | Reaiteka P.S. |  | R550,000.00 | 2012/13 |
|  |  | Kegomoditswe H.S |  | R900,000,00 | 2012/13 |
|  |  | Ditshipeng I.S. |  | R900,000.00 | 2012/13 |
|  |  | Gaaesi P.S. |  | R900,000.00 | 2012/13 |
|  |  | Dibotswa H.S. |  | R900,000.00 | 2012/13 |
| ADMIN BLOCK |  | Pulelo P.S. |  | R1,800,000.00 | 2012/13 |
|  |  | Glenred P.S. |  | R1,800,000.00 | 2012/13 |
| CLASSROOMS |  | Omang P.S.(5 new classrooms) |  | R1,800,000.00 | 2012/13 |
|  |  | Glenred P.S.(5 NEW CLASSROOMS) |  | R1,800,000.00 | 2012/13 |
| SCIENCE LAB |  | Bothitong H.S. |  | R1,600,000.00 | 2012/13 |
|  |  | Moshaweng S.S. |  | R1,600,000.00 | 2012/13 |
|  |  | Itlotleng H.S. |  | R1,600,000.00 | 2012/13 |
| MEDIA CENTRE |  | Nametsegang H.S. |  | R1,400,000.00 | 2012/13 |
|  |  | Oreeditse P.S. |  | R1,400,000.00 | 2012/13 |
| REPAIRS AND RENOVATIONS |  | Baduane P.S. |  | R1,000,000.00 | 2012/13 |
|  |  | Batshweneng I.S. |  | R1,000,000.00 | 2012/13 |
| FENCING |  | Perth P.S. |  | R750,000.00 | 2012/13 |
|  |  | Cardington P.S. |  | R750,000.00 | 2012/13 |
|  |  | Mahikaneng P.S. |  | R750,000.00 | 2012/13 |
|  |  | Logobate P.S. |  | R750,000.00 | 2012/13 |
|  |  | Gatalwatlou P.S. |  | R750,000.00 | 2012/13 |
|  |  | Itekeleng P.S. |  | R750,000.00 | 2012/13 |
| SASA |  | .600 Chairswere donated to be utilised by beneficiaries during pension payout to: - Bendel,Kikahela,Manyeding,Cassel,Penryn and Madularanch. - The region has targeted 40 paypoints to be improved. - Number of people accessing social services through ICROP:4500 - Number of identified poverty wards targeted through ICROP:33 poverty wards targeted. |  |  |  |
|  |  | Number of old age grant in payment:3033 |  | R3,639,600.00 |  |
|  |  | Number of war veteran: 6. |  | R7,320.00 |  |
|  |  | Number of Grants in AIDS: 166 |  | R46,480.00 |  |
|  |  | Number of disability Grant;2662 |  | R3,194,400.00 |  |
|  |  | Number of care dependency: 246 |  | R295,200.00 |  |
|  |  | Number of child support grant:5796 |  | R1,622,880.00 |  |

CASP PROJECTS :( R17 700 000)

| PROJECT | BUDGET | PROJECT TYPE | PROJECT ACTIVITIES | JOB CREATION & BENEFICIARIES |
| --- | --- | --- | --- | --- |
| Heuningvlei bulk water supply | R8,200 000 | Water infrastructure for livestock | - Water infrastructure(resevoirs,pipelines,drinking troughs)on Darnal Harrow,Ashfield. - Testing of boreholes (7) at:Darnal,Dekruis,Occedental Ranch9,Manaaneng 2,Greewhich ,and Upton. - Sightings for boreholes(9) at Leeds,Sydney,Taunton,CliftonGasport,Burford Leeds,Berwich,and Tyne - Line shaft pumps (3) at Harrow 1,Harrow 2 and Dekruis | 40 jobs Beneficiaries=150 M=100,F=25,Y=25 |
| Madibeng Stockwater | R4,000,000.00 | Water and fencing infrastructure for livestock | - Water infrastructure on the farms Leister,Abbey,Tweed,:sighting and drilling of boreholes (8) and equipping of boreholes (3) pipeline (16km ) - Fencing infrastructure(57km boundary fences) on the farms Leinster,Abbey,Tweed, Hull and Esher. | Jobs=30 M=18,F=3 Y=9 |
| Loopeng fencing and stock water project | R5 500 000 | Water and fencing infrastructure for livestock | - Water infrastructure sighting(6) on the farms sighting and drilling of boreholes (3) and equipping of boreholes (3) pipeline (5km )stock water system (3) - Fencing infrastructure(32km boundary fences and 43km internal fences) on the farms Magonate,Bunhill and Ganap/kelso. | Jobs =40 |
| Heuningvlei invader control | R120,000.00 | Control of invader plants | - Control 650 ha invader plants | Jobs=50 Beneficiaries M59,F=19,Y=5 |
| Ba Ga Bareki farm development | R6,000,000.00 | fencing infrastructure for livestock | - On the farms : Ashfield ,Darnal and Harrow ( 76 km boundary and 114 km internal fence) | Jobs=40 Beneficiaries=27 (F=2,M=20,Y=5) |
| FOOD SECURITY Ikageng vegetable project(Bendel) | R300 000 | Water and fencing infrastructure for vegetable project | - Testing of borehole and equipping borehole with windmill ;receilling of existing dam upgrading of foodplot fence | Jobs=6 Beneficiary=6 M=1,F=5 |
| Boitumelo Broiler (Cardington) | R160 000 | Production inputs for broiler project | - Production inputs:Day old chickens,feeds,broiler curtains | Jobs=15 Beneficiarie= 10 F=10 |
| A Ga Mmele | R200,000.00 | Water infrastructure and production inputs for vegetable projects | - Instalation of 2 water tanks,mono pump and water reticulation | Jobs= 15 Beneficiaries=15 M=4,F=11 |

BHP BILLITON

COMMUNITY INVESTMENT PROJECTS  FOR 2012/13 FY

| PROJECT NAME | OBJECTIVE | APPROVED BUDGET |
| --- | --- | --- |
| Maths and science educator development | Education development | R10 287 500 |
| Saturday School - learner support (site 1 & 2) | Education Development | R9 072 220 |
| School Chess programme | Primary Enrichment | R1 500 000 |
| Hotazel College | Capacity building | R14 456 631 |
| Hotazel Combined | Capacity building | R5 095 773 |
| Rearata Primary school | Infrastructure Development | R4 500 000 |
| Tsineng Road (Phase 1 & 2 ) | Infrastructure Development | R22 254 651 |
| Kuruman Hotazel Road | Infrastructure development | R20 000 000 |
| Youth HIV and AIDS | Supplementary Health | R3 420 000 |
| Business incubation centre | Capacity Development | R5 000 000 |
| Surprise Cattle farm | Agric farming | R6 350 000 |
| Gamorona Sand mine project | Small miners | R6 200 000 |

| PROJECT NAME | PUBLIC BENEFIT AREA | PROJECT VALUE |
| --- | --- | --- |
| Curriculum Teacher development and learner support - Sangari | Education and Skills Development | R15 402 397.50( JTG DEV. TRUST ) |
| Schools maths and Science – Augment Skills | Education and Skills Development | R18 180 307.00(JTG DEV. TRUST) |
| District Infrastructure Improvement project | Education and Skills Development | R18 000 000.00(JTG DEV.TRUST) |
| Health Quality Improvement Plan | Health Care | R 22 000 000.00 (JTG DEV. TRUST) |

DEPARTMENT OF SOCIAL DEVELOPMENT

| PROJECT | ACTIVITIES | BUDGET | PROGRESS | KEY CHALLENGES | RESPONSIBLE PERSONS/ ORGANISATION |
| --- | --- | --- | --- | --- | --- |
| - Construction of 5 x Early Childhood Development (ECD) centers in five villages -Segwaneng -Maphinick -Ncweng -Churchill -Kagung | - Construction of concrete structure - Completion date is the end of June 2012 | R9.6 million(Funded by JTG Developmental Trust | 80% complete | None | JTG Developmental Trust |
| - Construction of 5 x Home Communitiy Based Care (HCBC) centers in five villages -Cassel -Esperenza -Dithakong -Kanana -Seoding | - Construction concrete structure - Completion date is the end of June 2012 | R6.9 million(Funded by JTG Developmental Trust | 70 % complete | None | JTG Developmental Trust |
| - Construction of Dithakong Sub-Office | - Construction of pre-fabricated structure - Completion date is June 2012 | R2.1 million | 85% complete | The department is struggling to get Eskom to commit on the date for electricity connection to the building | Dept. of Public Works and Dept. of Social Development |
| - Establishment/construction of youth service centre in Bendel Village | - Procurement and renovation of the building to be used as accommodation for the centre | R200 000 | 30% complete | The dept. encountered some challenges to acquire a building in Bendel Village hence the delay to kickstart the project | Dept. of Social Development |
| - Establishment of Vegetables Gardens(Klein Neira Village and Ncwaneng Village) | - Fencing of gardens - Construction of storeroom - Procurement of gardening equipments - Cultivation of vegetables | Ncwaneng R584 000 Klein Neira R150 000 | 20% complete | The projects are still at the set-up stage(i.e fencing of the gardens e.t.c) | Dept. of Social Development BHPBilliton |
| - Balelapa Household Profiling | - Household profiling - Capturing of profiles - Generate Referrals(To be referred to relevant departments for service delivery intervention, for e,g if we find that many children in a certain village do not have birth certificates, home affairs is notified in the form of referrals to intervene by ensuring that outreach is conducted in that village to assist the children to apply for birth certificates) - War Room meetings sit on monthly basis to engage service delivery intervention reports submitted by various departments | R100 000 | 70% complete | Household Profilling finalized. The process to profile took longer than planned due to transport challenges. Only 55% of the profiles are captured in our system, the rest will be done before the end of June 2012. | Dept. of Social Development All Government Departments NGOs |
| - “Taking DSD to Communities” Project. (Note: This is a project spearheaded by office of the Deputy Minister: Social Development. It is aimed at targeting one town or village in each province and develop it with the assistance of other stakeholders to make a difference to socio-economic conditions of that community. Cassel Village has been identified in the Northern Cape as the focal point for this project) | - Meeting with the traditional leadership and community - Identification of community change agents and household change agents - Do a community profile. - Determine what projects are suitable for the development of the area and what measures to put in place to alleviate poverty and decrease unemployment. - Develop a Community Based Plan(CBP). The CBP is a document which clearly outlines development plans for the area with clear targets and timeframes. | -Leather Glove Making Project -Sewing Project -Create a Leader Project -Electrical Apprenticeship Programme -Old Age Home -Youth Service Centre | Community Profile done Community Based Plan done Income generating projects already identified | The dept. has managed to get companies to partner with community members to kickstart some income generating projects. The challenge however, is that we need to get seed funding to kickstart some of the projects. The other challenge is that we are struggling to acquire an unused building situated in Cassel Village owned by the North West Development Coorporation to use it to accommodate the identified projects since the village does not have infrastructure that can accommodate the said projects. The dept. will also need funds to renovate the building as it is currently in a very bad delapitated condition. | Community members themselves, Traditional Council, Government Departments, Municipalities, JTG Developmental Trust, Mining Houses, SEDA, and other stakeholders. |

DEPARTMENT OF SOCIAL DEVELOPMENT

| PROJECT | ACTIVITIES | BUDGET | PROGRESS | KEY CHALLENGES | RESPONSIBLE PERSONS/ ORGANISATION |
| --- | --- | --- | --- | --- | --- |
| - Construction of 5 x Early Childhood Development (ECD) centers in five villages -Segwaneng -Maphinick -Ncweng -Churchill -Kagung | - Construction of concrete structure - Completion date is the end of June 2012 | R9.6 million(Funded by JTG Developmental Trust | 80% complete | None | JTG Developmental Trust |
| - Construction of 5 x Home Communitiy Based Care (HCBC) centers in five villages -Cassel -Esperenza -Dithakong -Kanana -Seoding | - Construction concrete structure - Completion date is the end of June 2012 | R6.9 million(Funded by JTG Developmental Trust | 70 % complete | None | JTG Developmental Trust |
| - Construction of Dithakong Sub-Office | - Construction of pre-fabricated structure - Completion date is June 2012 | R2.1 million | 85% complete | The department is struggling to get Eskom to commit on the date for electricity connection to the building | Dept. of Public Works and Dept. of Social Development |
| - Establishment/construction of youth service centre in Bendel Village | - Procurement and renovation of the building to be used as accommodation for the centre | R200 000 | 30% complete | The dept. encountered some challenges to acquire a building in Bendel Village hence the delay to kickstart the project | Dept. of Social Development |
| - Establishment of Vegetables Gardens(Klein Neira Village and Ncwaneng Village) | - Fencing of gardens - Construction of storeroom - Procurement of gardening equipments - Cultivation of vegetables | Ncwaneng R584 000 Klein Neira R150 000 | 20% complete | The projects are still at the set-up stage(i.e fencing of the gardens e.t.c) | Dept. of Social Development BHPBilliton |
| - Balelapa Household Profiling | - Household profiling - Capturing of profiles - Generate Referrals(To be referred to relevant departments for service delivery intervention, for e,g if we find that many children in a certain village do not have birth certificates, home affairs is notified in the form of referrals to intervene by ensuring that outreach is conducted in that village to assist the children to apply for birth certificates) - War Room meetings sit on monthly basis to engage service delivery intervention reports submitted by various departments | R100 000 | 70% complete | Household Profilling finalized. The process to profile took longer than planned due to transport challenges. Only 55% of the profiles are captured in our system, the rest will be done before the end of June 2012. | Dept. of Social Development All Government Departments NGOs |
| - “Taking DSD to Communities” Project. (Note: This is a project spearheaded by office of the Deputy Minister: Social Development. It is aimed at targeting one town or village in each province and develop it with the assistance of other stakeholders to make a difference to socio-economic conditions of that community. Cassel Village has been identified in the Northern Cape as the focal point for this project) | - Meeting with the traditional leadership and community - Identification of community change agents and household change agents - Do a community profile. - Determine what projects are suitable for the development of the area and what measures to put in place to alleviate poverty and decrease unemployment. - Develop a Community Based Plan(CBP). The CBP is a document which clearly outlines development plans for the area with clear targets and timeframes. | -Leather Glove Making Project -Sewing Project -Create a Leader Project -Electrical Apprenticeship Programme -Old Age Home -Youth Service Centre | Community Profile done Community Based Plan done Income generating projects already identified | The dept. has managed to get companies to partner with community members to kickstart some income generating projects. The challenge however, is that we need to get seed funding to kickstart some of the projects. The other challenge is that we are struggling to acquire an unused building situated in Cassel Village owned by the North West Development Coorporation to use it to accommodate the identified projects since the village does not have infrastructure that can accommodate the said projects. The dept. will also need funds to renovate the building as it is currently in a very bad delapitated condition. | Community members themselves, Traditional Council, Government Departments, Municipalities, JTG Developmental Trust, Mining Houses, SEDA, and other stakeholders. |

PROJECTS  (unfunded)

| PR.NUM | PROJECT TYPE | PROJECT NAME | BRIEF DESCRIPTION | WARD | FUNDING BUDGET | BUDGET NEEDED |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Water | Convertion of prepaid stand pipes | Replacement of conlog and lesiratag prepaid stand pipes | all | none | R3,770,263.00 |
| 2 | Water | Installation of bulk water meters, - Phase 1 | Installation and replacement of bulk water meters at water extraction and supply points | all | none | R11,000,000.00 |
| 3 | Water | Installation of bulk water meters- phase 2 | Installation and replacement of bulk water meters at water extraction and supply points | all | none | R10,000,000.00 |
| 4 | Water | Water safety plan | Water quality | all | none | R450,000.00 |
| 5 | Water | Purchase of cherry pickers | Purchase of 2 cherry pickers for water quality purposes . | all | None | R617,500.00 |
| 6 | Water | Purchase of crane truck | Replacement of plastic water tanks and repair works on water tanks | all | None | R1,200,000.00 |
| 7 | Water | Water infrastructure refurbishment work programme | Replacement of 24x 10kl plastic tanks , 4 x tank stands ,28 lister foundations,28 litre engines and 16 x Pump houses fencing | all | R4,540,000.00 | R8,220,652.00 |
| 8 | Water | Klein Eifell water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 3 | None | R1,090,705.00 |
| 9 | Water | Sesipi Water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R1,755,433.00 |
| 10 | Water | Perth Water supply Scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R1,958,138.00 |
| 11 | Water | Kome water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R877,395.00 |
| 12 | Water | Tsiloane water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R644,214.00 |
| 13 | Water | Shalaneng water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R1,686,132.00 |
| 14 | Water | Heuningvlei water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R6,400,690.00 |
| 15 | Water | Makhubung water supply scheme | Connect bulk water supply scheme ,construction of elevated reservoir ,water reticulation upgrade and standpipes replacement | 1 | None | R3,363,919.00 |
| 16 | Water | Gadiboe Water reticulation,extention | Installation of water reticulation lines and replacement of stand pipes | 6 | None | R5,068,337.00 |
| 17 | Water | Maphiniki-bulk water supply-Phase 1 | Installation of water reticulation lines and replacement of stand pipes | 6 | Tshipi e ntle | R4,741,269.00 |
| 18 | Water | Maphiniki-bulk water supply-Phase 2 | Resource development and equipping ,installation of rising main water line reticulation lines. | 6 | None | R4,631,678.00 |
| 19 | Water | Saamsukkel pumpmain and booster pumpstation (phase 3) | Construction of pumpmain from Maphiniki to Saamsukkel and booster pumpstation | 6 | None | R3,112,918.00 |
| 20 | Water | Maphiniki-sportsfield water supply (phase 4) | Construction of mainline to Maphiniki sportsfield | 6 | None | R529,153.00 |
| 21 | Water | Drieloop and kganung water scheme | Source development ,equipping boreholes,construction of elevated reservoir ,water reticulation upgrade and water standpipes replacement | 15 | None | Not yet developed |
| 22 | Water | Gamaketlele extension | Improve water supply infrastructure and foresee for the village extension |  |  | NOT YET DEVELOPED |
| 23 | Water | Tlapeng water scheme | Tlapeng water scheme |  | None | R4,267,897.00 |
| 24 | Water | Kikahela 1 and 2 water scheme | Kikahela 1 and 2 water scheme |  | None | R12,452,072.00 |
| 25 | Water | Niks water scheme | Niks water scheme |  | None | R5,030,169.00 |
| 26 | Water | Makgaladi water scheme | Makgaladi water scheme |  | None | R4,502,621.00 |
| 27 | Water | Motlhoeng water scheme | Motlhoeng water scheme |  | None | R7,001,725.00 |
| 28 | Water | Radiatsongwa water scheme | Radiatsongwa water scheme |  | None | R6,263,391.00 |
| 29 | Water | Gakhoe and Gamotsokwane water scheme | Gakhoe and Gamotsokwane water scheme |  | None | R17,794,513.00 |
| 30 | Water | Water Aar Water scheme | Water Aar Water scheme |  | None | R5,255,600.00 |
| 31 | Water | Cassel,Glenred,and Kganoane bulk water | Cassel,Glenred,and Kganoane bulk water |  | None | NOT YET DEVELOPED |
| 33 | Water | Kortnight water scheme | Kortnight water scheme |  | R1,500,000.00 | R1,500,000.00 |
| 34 | Water | Kruis Aar water scheme | Kruis Aar water scheme |  | None | R4,391.491;00 |
| 35 | Water | Mosekeng water scheme | Mosekeng water scheme |  | None | R3,036,622.00 |
| 37 | Water | Magojaneng west Water scheme | Magojaneng west Water scheme |  | None | R11,210,609.00 |
| 38 | Water | Masankong water scheme | Masankong water scheme |  | None | UNDETERMINED |
| 41 | Water | Kokonye water scheme | Kokonye water scheme |  | None | R5,118,845.00 |
| 42 | Water | Kiangkop water supply scheme improvement | Improve water supply infrastructure and foresee for the village extension |  | None | NOT YET DEVELOPED |
| 43 | Water | Bendel water storage improvement | Replace the current storage with elevated steel tank water storage |  | R5,516,000.00 | R6,501,000.00 |
| 44 | Water | Vanzylsrus water source augmentation | Additional borehole /s (water source) establishment ,equipping and connecting to rising main water line. |  | R2,000,000.00 | R2,700,000.00 |
| 45 | Basic housing | Low cost houses construction | Construction of houses for basic needs |  | None | R499,064.000.00 |
| 46 | Roads | Village street house construction | Construction of village street roads and related storm water infrastructure | all | None | R1,709,349,863.00 |
| 47 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage | 1 | None | R8,686,000.00 |
| 48 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage |  | None | R1,474,600.00 |
| 49 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(Magwagwe) | 15 | None | R2,009,900.00 |
| 50 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(Ntswelengwe) | 15 | None | R2,424,000.00 |
| 51 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(Camden) | 13 | None | R5,080,300.00 |
| 52 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(diwatshane) | 9 | None | R717,100.00 |
| 53 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(Glenred) | 10 | None | R5,888,300.00 |
| 54 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(Dithakong) | 12 | None | R8,201,200.00 |
| 55 | Sanitation | Rural sanitation programme | Construction of VIP(dry sanitation) health and hygiene education on usage(Bendel) | 8 | None | R6,181,200.00 |
| 56 | Street lighting | Tsineng and Gadiboe high mast project | Construction of high mast light | 5,6 | None | R6,433,700.00 |
| 57 | Street lighting | Heuningvlei high mast project | Construction of high mast light | 1 | None | R8,686,000.00 |
| 58 | Street lighting | Manyeding and Ntswelengwe high mast project | Construction of high mast light | 15 | None | R5,060,100.00 |
| 59 | Street lighting | Deurward and Bendel high mast project | Construction of high mast light | 7,8 | None | R8,251,700.00 |
| 60 | Street lighting | Dithakong ,Glenred high mast project | Construction of high mast light | 1112 | None | R24,936,900.00 |
| 61 | Street lighting | Ganap and Laxey high mast light project | Construction of high mast light | 2,3 | None |  |
| 62 | Basic playground | Cassel sportsfield | Concrete slab fencing and ablution block |  | None |  |
| 63 | Basic playground | Bendel sportsfield | Concrete slab fencing and ablution block | 8 | None |  |
| 64 | Basic playground | Metswetsaneng sports field | Concrete slab fencing and ablution block |  | None |  |
| 65 | Basic playground | Loopeng sportsfield | Concrete slab fencing and ablution block | 3 | None |  |
| 65 | Basic playground | Glenred sportsfield | Concrete slab fencing and ablution block | 10 | None |  |
| 66 | sportsfield | Dithakong sportsfield | Construction of concrete slab fence , pavilion and high mast light | 12 | None |  |
| 67 | sportsfield | Laxey Sportsfield | Construction of concrete slab fence , pavilion and high mast light | 3 | None |  |
| 68 | sportsfield | Maphiniki Sportsfield | Construction of concrete slab fence , pavilion and high mast light | 6 | None |  |
| 69 | sportsfield | Penryn sportsfield | Construction of concrete slab fence , pavilion and high mast light | 3 | None |  |

| SOCIAL AND LABOUR PLAN PROJECTS - TARGETED TO COMMENCE ON YEAR 1 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Ward | Village | In IDP | Targeted year | Project Name/Discription | Budgect Needed |
| Spatial palnning & Housing | All Wards |  | √ | 1 | compilation of status quo and spatial framework development(phase 1) | R 253 968.00 |
|  |  |  | √ | 2 | compilation of status quo and spatial framework development(phase 2) | R 546 032.00 |
|  | All Wards |  | √ | 1 | Housing Survey needs (phase 1) | R 993 058.00 |
|  |  |  | √ | 2 | Housing Survey needs (phase 2) | R 530 642.00 |
| Water projects | All Wards |  | √ | 1 | Installation of bulk water meters- (WC&DM) - phase 1 | R 11 000 000.00 |
|  | All Wards |  | √ | 2 | Installation of bulk water meters- (WC&DM) phase2 | R 10 000 000.00 |
|  | All Wards |  | √ | 2 | Water Safety Plan (Water Quality) | R 450 000.00 |
|  | All Wards |  | O&M | 1 | Purchase of 3 cherry pickers for water quality purposes and other maintenance works | R 926 250.00 |
|  |  | Kome | √ | 1 | Kome water reticulation upgrade & elevated storage | R 877 395.00 |
|  |  | Tsiloane | √ | 1 | Tsiloane water reticulation upgrade & elevated storage | R 644 214.00 |
|  |  | Shalaneng | √ | 2 | Shalaneng water reticulation upgrade & elevated storage | R 1 626 132.00 |
|  |  | Heuningvlei | √ | 2 | Heuningvlei water reticulation upgrade & elevated storage | R 7 400 690.00 |
|  |  | Makhubung | √ | 2 | Makhubung water reticulation upgrade & elevated storage | R 2 003 919.00 |
|  |  | Bendel |  | 1 | Bendel elevated water storage improvement | R 1 666 483.64 |
| Roads & bridges | all wards |  | √ | 1 | village street roads network feasiblity and RMS | R 1 700 000.00 |
|  |  | one of the provincial roads |  | 1 | construction of a 7 km tar road road | R 20 000 000.00 |
|  | all wards |  |  | 1 | gravel patch work maintenance team plant - 2x tipper trucks, 1xtlb, selfpropelled roller, motor grader, water tanker | R 7 650 000.00 |
|  |  | Bendel | √ | 1 | Street village road construction (phase 2) | R 3 102 125.26 |
|  |  | Maphiniki | √ | 1 | Street village road construction (phase 2) | R 2 969 578.69 |
|  |  | Deorham | √ | 1 | 2.5 km tar road | R 7 050 000.00 |
| Street lighting (consider solar ) |  | Tsineng & Gadiboe |  | 1, 2 or 3 |  | R 5 736 200.00 |
|  |  | Heuningvlei |  | 1, 2 or 3 |  | R 5 244 000.00 |
|  |  | Manyeding & Ncoelengwe |  | 1, 2 or 3 |  | R 1 803 200.00 |
|  |  | Deurward & Bendel |  | 1, 2 or 3 |  | R 5 244 000.00 |
|  |  | Dithakong, Glenred & Cassel |  | 1, 2 or 3 |  | R 10 160 250.00 |
| Social , recreation & tourism |  | Dithakong |  | 1 | Dithakong - lighting | R 1 000 000.00 |
|  |  | Maphiniki |  | 1 | Maphiniki -Pavilion & concrete slabs fencing and mast lights | R 3 200 000.00 |
|  |  | Laxey |  | 1 | Laxey - mast lights and greenifying | R 1 200 000.00 |
| Enterprises | Dithakong |  |  | 1 | Intergrated Energy Centre condition assesment verification and support | R 1 000 000.00 |
|  |  |  |  | 1 | Charcoal manufacturing enterprise | R 4 900 000.00 |
|  |  |  |  |  |  | R 225 238 518.57 |

RUNNING PROJECTS:

| PROJECT | PROJECT DESCRIPTION | LOCATION | FUNDER | APPROVEDBUDGET |
| --- | --- | --- | --- | --- |
| Maipeing Water reticulation | 6km of water reticulation,source development , 2 new boreholes and 17 additional standpipes,3 km Pump main | Maipeing | MIG | R6,286,431.18 |
| Madibeng Water reticulation | Source development 3 new boreholes 2,5km pump main,100kl Elevated storage Tank, Refurbishment and Extentsion of the Current Reticulation network for 12km. Additional of 10 Communal standpipes | Madibeng | ASSMANG BLACK ROCK MINES | 6 800 000.00 |
| Gatswinyane Water Supply-Reticulation | 24.8 of Water Reticulation, 57 Additional Communal standpipes, Connect to the Existing Ditshipeng Bulk line | Gatswinayane | MIG W/NC/5875/08/10 | 8 597 774.25 |
| Ga-Rapoane Water Supply-Reticulation | 19.4 km of Water Reticulation, 20 new pre-paid stand pipes, Supply and Erect 200 kl pressed steel tank on al 15 m tank stand | Ga-Rapoane | Waiting for MIG Registration | 10 353 021.87 |
| Mokala Wa Noga Water Supply Reticulation | 2.1 km of Water Reticulation, 7 new prepaid stand pipes and 2 new boreholes with positive Displacement pumps, Supply and Erect 100 kl pressed steel tank on a 15m tank stand | Mokala Wa Noga | Waiting for MIG Registration | 4 518 846.99 |
| Heuningvlei Bulk Water Scheme | Phase 1. Refurbishment of 7 Existing boreholes, Construction of new Booster Pump station and 3.5 km Pumping Main, Refurbishment of Existing Concrete Reservoir, Refurbishment Existing pipe | Heuningvleil | DWA RBIG-REGIONAL Bulk Infrastructure Grant | 23 000 000.00 |
| Supply and Delivery supervision of sanitation Unit (sealed pit) | Supply Delivery and supervision to Various Village within the Joe Morolong Municipal Area, Bothitong & Coe | Various Villages within the Joe Morolong Municipal AREA, Bothitong & Coe | MIG/NC0064/S/06/09 | 7 921 454.03 |
|  | Supply Delivery and supervision on Various Villages withn the Joe Morolong Municipal Area, Madibeng (616), Glenred (983), Metswetsaneng (146), Ntswelengwe (240) | Madibeng | MIG/NC0064/06/09 | 6 228 068.00 |
|  |  | Ntswelengwe and Metswetsaneng | MIG/NC0064/S/06/10 | 3 657 241.92 |
|  |  | Glenred | MIG/NC0064/S/06/11 | 8 767 573.60 |
| 820: Ward 1-15 Municipal Roads |  | Upgranding of internal roads to Various Village within the Joe Morolong Municipal Area, Makhubung; | MIG/NC0106/R,ST/06/07 | 12 039 354.00 |

5.1	Operational Strategies and Programme Integration

After designing the projects, Joe Morolong had to make sure that the designed projects correlate with the initial needs of the community and fall within the existing resource frames and legal requirements.  After securing this, it finalized its first draft IDP by compiling integrated programmes.  These programmes deals with the following issues and the final programmes are reflected in this document:

- Water and Sanitation – Water Sector Development Plans

- Municipal Finances – 3-Year Financial Plan of the Municipality

- Cost of all the projects – 3-Year Capital Investment Programme

- Actions to implement these projects 3 –Year Action Programme

- Performance of the Municipality – Integrated Monitoring and Performance Management System

- Spatial presentation and Analysis of issues – Spatial Development Framework

- Poverty and Gender Equity – Integrated Poverty Reduction and Gender Equity Programme

- Environment and Development – Integrated Environmental Programme

- Economic Development – Integrated LED Programme

- Institutional Capacity – Integrated Institutional Programme

- HIV/AIDS – Integrated HIV/AIDS programme

- Disaster Management – Disaster Management Plan

5.1.1	Water Sector Plans

The Water Sector Plans of this Municipality forms part of the bigger Water Services Development Plan (WSDP) drafted by the District Municipality.  Due to capacity constraints the task of drafting these was a joint effort between the District Municipality,  ( which was the then water service provider in Joe Morolong. At the point of compiling the first IDP document no sector plans were completed.  This was due to the late start by the District Municipality with its WSDP.   However, the draft WSDP is completed and available from the municipal offices.  Due to the huge water and sanitation backlog currently experienced in this Municipality, the sector plan is seen as a crucial part of the IDP process and the WSDP.  This view of the Municipality resulted in the sector plan being done within the IDP process, informing the IDP process and visa versa.

5.1.2	Financial Plan for the Municipality

The municipality is currently performing its own financial management, which include the day – to – day functions such as income and expenditure control, recording and safekeeping of financial records and asset management.

As a result of the identified municipal challenges facing local authority, improvements have been seen in that regard through the service level agreement signed between the District and Joe Morolong  Local Municipality. There was a support through Provincial Local Government on training of councillors, ward committees and officials. Ward committees and officials were trained on issues related to governance, municipal by – laws budgets and other legislation requirements.

- Budgets

Annual budgets are prepared and made available to communities and other stakeholders for inputs and comments. Budget forums are established and normally meet with sector departments for proper planning and reporting. Annual review of budget and IDP is also carried out to ensure that expenditure on projects is limited to funds confirmed and available.

- Revenue and Expenditure .

1.        INCOME   SUMMARY

- PROPERTY RATES                                               R 10,410,670.00

- SERVICES CHARGES                                            R12,331,843.00

- OTHER INCOME                                                    R413,755.00

- INTEREST ON INVESTMENT                            R1,200.000.00

- EQUITABLE SHARE                                             R72,127,000.00

- WSOG                                                                      R1,875,000.00

TOTAL  :                                                                   R98,358,268.00

2.  OPERATIONAL   GRANTS

DIRECT ALLOCATION

- EPWP                                                    R1,000,000.00

- EQUITABLE SHARE                          R72,127,000.00

- WSOG                                                    R1,875,000.00

- FMG                                                        R1,500,000.00

- MSIG                                                       R800,000.00

- TOTAL OPERATING GRANT:           R77,302,000.00

3.CAPITAL GRANTS

- MIG                          : R56,479,000,00

- EXPENDITURE SUMMARY

- EMPLOYEES COSTS                     R26,011,509.00

- COUNCILLORS REMUN.              R7,204,487.00

- IMPAIRMENT LOSSES                 R158,850.00

- DEPRECIATION                              R1,151,984.00

- REPAIR & MAINT.                         R10,533,534.00

- BULK PURCHASE                          R6,988,734.00

- LOAN REPAYMENT                      R649,000.00

- CONTRACTED SERVICES            R5,855,094.00

- FREE BASIC                                     R1,749,943,00

- GRANTS PAID                                 R52,700.00

- GENERAL EXPENSE                      R24,971,943.00

TOTAL :                                             R 85,337,804.00

- MIG BREAKDOWN

- WATER                                          R14,426,823.00

- SANITATION                                 R24,985,163.00

- ROADS                                            R7,635,021.00

- SPORTS & RECREATION           R8,302,413.00

- PMU                                                  R1,129,580.00

Table: Forecast: Capital expenditure and source of financing

| CAPITAL EXPENDITURE | 12/13 |
| --- | --- |
| Infrastructure (Water) | R 15,126,823.00 |
| Sanitation | R 24,985,163.00 |
| Roads | R 7,635,021.00 |
| Traffic phase 1 | R 320,000.00 |
| SPORTS & RECREATION | R 8,302,413 |
| Cemeteries | R 267,364.00 |
| Kiang Kop(cultural village) | R 3,500,000.00 |
| Vehicles | R 3,801,200.00 |
| Computers & Printers | R 397,000.00 |
| Office furniture | R 100,000.00 |
| Buildings (Technical) | R 2,500,000.00 |
| Partitioning (offices) | R 400,000.00 |
| Other (vehicle) | R 50,000.00 |
| Video Camera | R 5,000.00 |
| Software Upgrade | R 80,000.00 |
| Web site | R 150,000.00 |
| Refuse Vehicle | R 750,000.00 |
| TOTAL | R68,369,984.00 |

RECONCILIATION OF IDP OBJECTIVES AND BUDGET ( REVENUE)

| STRATEGIC OBJECTIVE | GOAL | BUDGET YEAR 2012/13 | BUDGET YEAR 2013/14 | BUDGET YEAR 2014/15 |
| --- | --- | --- | --- | --- |
| Financial Viability and sustainability | Improved budgeting ,revenue generation & protection, debtors control grow and diversity revenue and value for money expenditure through an integrated financial plan | R89,768,000.00 | R100,297,000.00 | R11,168,000.00 |
| Provision and maintenance of municipal services | Ensure the provision and maintenance of municipal service delivery | R56,509,000.00 | R59,608,000.00 | R64,610,000.00 |
| Decrease unemployment rate over 5 years and increase economy by 5%. | Encourage communities to establish income generating project and provide support to SMMEs | R1,019 ,000.00 | R19,000.00 | R19,000,00 |
| Access to good quality drinking water supply system | Implement the existing tariff system and cost recovery | R7,019,000.00 | R5,415,000.00 | R5,678,000.00 |
| To ensure a component ,efficient and effective municipal administration | annually review and update the human resource policies and skills development plant. | R180,000.00 | R187,000.00 | R194,000.00 |
| Municipal institutional Development and Transformation | Addressing Auditor General queries as per the action plan to ensure improvement in audit opinion.Firm up on performance management system.Managing the interface between the administrative and political structures. | R3,642,000.00 | R4,617,000.00 | R5,430,000.00 |
| TOTAL REVENUE |  | R158,137,000.00 | R170,143,000.00 | R187,099,000.00 |

RECONCILLIATION OF IDP STRATEGIC OBJECTIVES AND BUDGET  (OPERATING EXPENDITURE)

| STRATEGIC OBJECTIVE | GOAL | BUDGET YEAR 2012/13 | BUDGET YEAR 2013/14 | BUDGET YEAR 2014/15 |
| --- | --- | --- | --- | --- |
| Financial Viability and sustainability | Improved budgeting ,revenue generation & protection, debtors control grow and diversity revenue and value for money expenditure through an integrated financial plan | R8,599,000.00 | R9,048,000.00 | R17,540,000.00 |
| Provision and maintenance of municipal services | Ensure the provision and maintenance of municipal service delivery | R11,038,000.00 | R11,615,000.00 | R12,237,000.00 |
| Decrease unemployment rate over 5 years and increase economy by 5%. | Encourage communities to establish income generating project and provide support to SMMEs | R7,688,000.00 | R8,091,000.00 | R8,489,000.00 |
| Access to good quality drinking water supply system | Implement the existing tariff system and cost recovery | R25,057,000.00 | R26,989,000.00 | R28,989,000.00 |
| To ensure a component ,efficient and effective municipal administration | annually review and update the human resource policies and skills development plant. | R14,404,000.00 | R14,329,000.00 | R15,051,000.00 |
| Municipal institutional Development and Transformation | Addressing Auditor General queries as per the action plan to ensure improvement in audit opinion.Firm up on performance management system.Managing the interface between the administrative and political structures. | R19,680,000.00 | R22,624,000.00 | R15,559,000.00 |
| TOTAL REVENUE |  | R86,467,000.00 | R92,697,000.00 | R97,308,000.00 |

RECONCILLIATION OF IDP STRATEGIC OBJECTIVES AND BUDGET (CAPITAL EXPENDITURE)

| STRATEGIC OBJECTIVE | GOAL | BUDGET YEAR 2012/13 | BUDGET YEAR 2013/14 | BUDGET YEAR 2014/15 |
| --- | --- | --- | --- | --- |
| Financial Viability and sustainability | Improved budgeting ,revenue generation & protection, debtors control grow and diversity revenue and value for money expenditure through an integrated financial plan | R70,000.00 | ----- | ------- |
| Provision and maintenance of municipal services | Ensure the provision and maintenance of municipal service delivery | R43,690,000.00 | R9,040,000.00 | R47,092,000.00 |
| Decrease unemployment rate over 5 years and increase economy by 5%. | Encourage communities to establish income generating project and provide support to SMMEs | R3,762,000.00 | R15,852,000.00 | R8,748,000.00 |
| Access to good quality drinking water supply system | Implement the existing tariff system and cost recovery | R17,593,000.00 | R49,628,000.00 | R16,494,000.00 |
| To ensure a component ,efficient and effective municipal administration | annually review and update the human resource policies and skills development plant. | R750,000.00 | R210,000.00 | R225,000.00 |
| Municipal institutional Development and Transformation | Addressing Auditor General queries as per the action plan to ensure improvement in audit opinion.Firm up on performance management system.Managing the interface between the administrative and political structures. | R2,505,000.00 | -------- | ----------- |
| TOTAL REVENUE |  | R68,370,000.00 | R74,730,000.00 | R72,559,000.00 |

5.1.3	3-Year Capital Investment Programme

In developing the 3-Year Capital Investment Programme, it is interesting to note that most of the investment is needed in infrastructure related projects, i.e. electricity, roads, water and sanitation.  This is a reflection on the backlog in terms of these services in Joe Morolong

The roads in this Municipality are widely recognised as being in a very poor condition.  This is influencing the mobility of the community and indirectly influencing the poverty levels.  The proposed projects, needing huge investments, are therefore seen as a real effort of this Municipality to positively influence the lives of its residents.

Although electricity is generally not seen as a part of basic services, it is considered by the community as very critical in order to improve their livelihood. Due to the involvement of ESKOM in the IDP process, indicating their ability to electrify the area within the available resources, it is predicted that 100% of household communities in Joe Morolong in need of extension and in fills will be covered. Basic health services are also a great concern to the community.  Therefore the relatively high investment needed in this sector compared to some of the other issues.

The total capital investment needed for IDP projects in this Municipality is very high.  It is acknowledged by this Municipality that it is most unlikely for it to receive all the necessary funding to implement all the projects.  However, it does provide a realistic picture of the backlog in terms of services and facilities and the general high poverty levels of the community.   Using this IDP as a guideline, investment will go into the right areas of the Municipality.

5.1.4	Monitoring and Performance Management System

In terms of requirements to comply with certain legislative provisions we are rated as low capacity municipality. We were therefore not required to comply with certain legislative requirements, for instance in relation to Performance Management System as a low capacity municipality we were only required to put in place our Performance Management System by the financial year 2011/12.

Despite the fact that we were only required to comply by the 2011/12 financial year we however began with this process as far back as the year 2004, and it was fully put in place as from the beginning of 2012/13 financial year.

On annual basis we now ensure that the Performance Management System Framework/Policy, Corporate Strategy, and Departmental Technical SDBIPs’ are adopted by Council and are implemented. Performance Contracts for the Municipal Manager and Other Section 57 Managers are also signed annually. Performance management will also be applied to level 6, 7 and 8 in a near future.

Departmental Performance Reports are submitted to Council on Quarterly basis, and the Annual Performance Report of the Municipality is submitted to DPLG as required.

5.1.5	Spatial Development Framework

The Spatial Development Framework (SDF) of this Municipality is reviewed and will be completed at the end of 2012/2013 and subsequently will form part of this IDP new Document.  This was one of the few programmes outsourced by the Municipality. Due to its size, the SDF would not be included in this document, but for further information on the SDF, the Joe Morolong Local Municipality could be contacted. During 2005/2006 financial year, this framework was reviewed and adopted by council. There is the new SDF which is developed and soon it will be adopted by the council.

5.1.6	Integrated Poverty Reduction and Gender Equity Programme

Currently this Municipality does have a poverty alleviation programmes within the LED section.However there are a number of designed projects that influence poverty reduction or are influenced by gender equity.  These projects form a good basis for this Municipality to develop programmes and it indicates the efforts of this Municipality dealing with these 2 issues.

This Municipality does consider national policies and frameworks when it comes to these issues.  This implies that during any tender procedure and appointment of new staff members, gender equity is considered and policies are adhered to.

As discussed under the 3-year Capital Investment Programme the emphasis will be much on poverty alleviation for the next 3 years.  Most of the investment is needed in services and basic health, directly impacting poverty in a positive manner.  The Joe Morolong area is one of the poorest in the country hence it has been identified as a Presidential Node under the new CRDP programme.  This also suggests the importance of poverty alleviation in the Municipality.

The projects affecting poverty and gender are therefore of utmost importance to this Municipality and suggest a poverty alleviation “programme” for this Municipality.

5.1.7	Integrated Environmental Management Programme

The Integrated Environmental Management Programme has been developed and adopted by council.

5.1.8	Integrated Local Economic Programme

(i) 	Establishment progress:

The Local Economic Development Manager is been appointed. This will substantially assist in bettering environment for the LED establishment to fully effect.

- Governance progress:

The Local Economic Development and Tourism Strategy has been developed and got the due adoption by Municipal Council. This document is important in giving guidance and framework for the smooth rolling-out of the Local Economic Development.

Most of the projects could not effect due to internal capacity limitations and inadequate funding. It is therefore critical to indicate a need to beef-up the division structure with an additional one Junior Economist, Tourism Officer, and three Interns, with a view of equating the human resource to the work scope.

It is further critical that we create a better coordination of LED efforts by different role players i.e. Provincial Sector Departments (Agriculture, Economic Affairs, Tourism and Education), John  Taolo District Local Economic Development, , Joe Morolong Finance: Procurement, Integrated Development Plan, Technical Division, Community Services - Youth Development Unit, Woman Development Programme, Disabled Persons Programme. However, there is still no clear distinction of roles among these role players. As a result, there need to hold a Role-player Effort Coordination Workshop.

Small Medium and Micro Entrepreneurial Development Programme should be undertaken, with an objective of giving the potential entrepreneurs support to take advantage of the business opportunity presented by our locality in both private and public sectors. To that end there shall be a setup of SMME Support Desk, catering for a wide range of support activities, including training and mentoring.

# Projects

We envisage undertaking the following projects in future

Table: Envisaged Led Projects

| No. | Programme | Scope | Projects |
| --- | --- | --- | --- |
|  | Improvement of Community Based Economic Sector | Across the whole Municipality | - Functional Rural Service Centre Development. - Formation of Farming Cooperatives: Livestock and Poultry Improvement (Dipudi Project, Ostrich Farming Cooperative, Poultry Farming) - Formation of Farming Cooperatives: Crop Production Improvement (Manyeding Cultivation Project) - Formation of Business Cooperatives: Integrated Energy Centres (Dithakong and Laxey) Leather Tanning Corporative, and Small Scale Mining (Minerals and Sand) - Tourism Sector Development (Kiang Kop and Bothithong Cultural Home, Game Hunting and Farming Enterprise) - Agricultural Infrastructure Development (Farming Camps Demarcation, Caring Facilities Improvement, Water Supply Infrastructure Improvement) - Economic Markets Development - Human Capital Investment (Tertiary Education Bursary Scheme) |

The progression towards a wholly established LED Division of our Municipality is on the right course. We are further reasonable assured of a fast growth and development of this programme to the end of the current financial year.

The succeeding financial year will find the division on a very good stead to can carry the municipal mandate to the expected end.

The Municipality identified specific LED projects, including some of the CRDP projects dealing with LED.  These identified projects will serve as basis for an LED programme and is also an indication of the effort of this Municipality dealing with this issue.

However, more emphases should be on commercializing livestock farming hence it is considered the major income generating sphere.

5.1.9	Integrated Institutional Programme

Joe Morolong Local Municipality was established on the 6th December 2000 under the name”Moshaweng” which is now called Joe Morolong`Named after our hero:Taolo Joseph Morolong who was born at Ditshipeng Village on July the1st 1927.The biography of the late Joe Morolong is within the profile of the municipality.

1. By then there were only five (5) officials and the Municipal Manager was seconded from John Taolo Gaetsewei District Municipality . The municipality was faced with enormous challenges given the fact that it had to start from scratch with lack of both Human and Infrastructural Resources. The municipality did not even have its own offices to operate from.

John Taolo Gaetsewe District Municipality was nominated by the State President as a CRDP nodal point mainly due to the rural nature and service delivery backlogs of Joe Morolong Local Municipality. Joe Morolong Municipality therefore became a focal point of CRDP programs.

The municipality has grown considerably since its establishment. There has been a lot of improvement in terms of infrastructural development and staffing. We moved to our own offices situated in Churchill Village in December 2004. After relocation to our new offices we then intensified the process of recruitment and selection of new staff. We have grown from staff complement of six (6) in the year 2001 to fourty two (42) currently in the year 2009.To this date, it complements STAFF OF 151 .(130 ON THE PAYROLL AND 21 on temporary basis )

An Integrated Institutional Programme is crucial in its effort to ensure effective local government, service delivery and implementation of this IDP.

The Institutional Programme can be broken up into Human Resources and Infrastructure.

- Human Resources

ORGANOGRAM

The first time an organogram was approved by Council was in 2004. Every year the organogram is reviewed to cater for service delivery and administrative demands. Placement of staff was finalized and approved by Council in 2012 and is still an ongoing process which is undertaken when the need arise annually..

EXISTING STAFF MEMBERS

Currently staff complement stands at  151

Filling of Vacant Positions

There are less than 10 vacant positions in the organogram.. There is a  dire need to urgently fill vacant positions in the Technical Services(e.g. town planner) Department due to the fact that implementation of projects has to be carried by ourselves. We are in the process of filling more vacant positions to improve service delivery capacity.

Capacity Building and Training

Training of Councillors and Officials is seen as part of human resource development in this Municipality. Skills Audit of Councillors and Officials is carried out to determine skills gap before the development of the Skills Development Plan. Skills Audit assists us to determine training intervention to be provided to an individual as part of human resource development.

The first Skills Development Plan of the Municipality was adopted by Council in the year 2006. The second one was adopted by Council in 2008 and is currently being implemented.

- Infrastructure

Municipal Offices have been constructed and are situated in Churchill village which is about 20 kilometres away from Kuruman Town. Community Hall has been built inside the municipal office yard.

The construction of Council Chamber was completed in 2007.

5.1.10	Integrated HIV and AIDs Programme

Currently, the Joe Morolong Local Municipality is having the Integrated HIV and AIDS policy.

#### Background

The impact of HIV and AIDS related illnesses and deaths are already obvious in hospitals.  The number of deaths due to AIDS will rise dramatically to almost a quarter of a million people per year within three years, where the average life expectancy is expected to fall from 60 years to about 40 years in 2010.  There will be nearly a million children under the age of 15 who will have lost their mothers to AIDS.  (Tool kit for Local Government).  Joe Morolong Municipality therefore commits itself to initiate its response to the epidemic and defines its role in the partnership against HIV and AIDS.

##### HIV and Aids Programme for Joe Morolong Local Municipality

Although the lack of information made it very difficult for this Municipality to deal with the issue during the IDP process it still managed to develop strategies and projects on the issue.  It was also identified by the Municipality as one the critical issues for the 5 years planning period. In responding to the above mentioned challenge.

5.1.11	Disaster Management Plan

During the council meeting on the 27 February 2008, the Disaster Operational Plan was approved and accepted for implementation by council. For now it needs to be reviewed.

5.1.12	Waste Management Plan

The Waste Management Plan has been developed.

5.1.12	Transport Plan

This will be shared with the district.

SMART = Specific, Measurable, Attainable, Results-orientated and Time-bound. Strategic objectives will be aligned to performance indicators and targets as required in terms of the Municipal Systems Act, 2000 and the Municipal Planning and Performance Management Regulations, 2001.